## Measurements 75 units
NEVO TOWER PER FLOOR
FLOOR # | Height | Width | Length | Floor Plate GSF | Unit Size NSF | Units / Floor | USE | Lobby Common Area GSF | Mikvah @ cost GSF | Synagogue @ cost GSF | Parking Common Area GSF | Gym - Amenities Common Area GSF | Pool Common Area GSF | Restaurant GSF | Commercial GSF | Residential GSF | Residential Hospitality GSF | GSF Floor | Synagogue - Mikvah Saleable @ Cost NSF | Saleable Restaurant NSF | Saleable Commercial NSF | Saleable Residential NSF | Saleable Residential Hospitality NSF | Non-Saleable Common areas NSF | Floor Usable NSF | Structural GSF | Total Floor GSF | Total GSF Floors 2-23 exluding floor 1 and the roof
1 | 20 | 75 | 175 | 13125 | 2625 | 4 | 2 Retail / Mikvah / Lobby | 1640.625 | 3281.25 | [5 empty] | 8203.125 |  |  | 13125 | 2625 |  | 6562.5 |  |  | 1312.5 | 10500 | 2625 | 13125
2 | 12 | 90 | 175 | 15750 | 12600 | 1 | Chabad |  |  | 15750 | [7 empty] | 15750 | 12600 | [5 empty] | 12600 | 3150 | 15750 | 15750
3 | 8.25 | 90 | 175 | 15750 | 247.0588 | 51 | Parking - EV Stations / ADA |  |  |  | 15750 | [6 empty] | 15750 | [5 empty] | 12600 | 12600 | 3150 | 15750 | 15750
4 | 8.25 | 90 | 175 | 15750 | 247.0588 | 51 | Parking - EV Stations / ADA |  |  |  | 15750 | [6 empty] | 15750 | [5 empty] | 12600 | 12600 | 3150 | 15750 | 15750
5 | 8.25 | 90 | 175 | 15750 | 247.0588 | 51 | Parking - EV Stations / ADA |  |  |  | 15750 | [6 empty] | 15750 | [5 empty] | 12600 | 12600 | 3150 | 15750 | 15750
6 | 10 | 70 | 155 | 8850 | 885 | 8 | Residential Hospitality Suites Flex 2 bed/2bath - sleep 6 | [9 empty] | 8850 | 8850 |  |  |  |  | 7080 |  | 7080 | 1770 | 8850 | 8850
6 |  |  |  | 2000 | 1600 | 1 | Gym/Amenities |  |  |  |  | 2000 | [5 empty] | 2000 | [5 empty] | 1600 | 1600 | 400 | 2000 | 2000
7 | 10 | 70 | 155 | 10850 | 2170 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 10850 |  | 10850 |  |  |  | 8680 |  |  | 8680 | 2170 | 10850 | 10850
8 | 10 | 70 | 155 | 10850 | 2170 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 10850 |  | 10850 |  |  |  | 8680 |  |  | 8680 | 2170 | 10850 | 10850
9 | 10 | 70 | 155 | 10850 | 2170 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 10850 |  | 10850 |  |  |  | 8680 |  |  | 8680 | 2170 | 10850 | 10850
10 | 10 | 70 | 155 | 10850 | 2170 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 10850 |  | 10850 |  |  |  | 8680 |  |  | 8680 | 2170 | 10850 | 10850
11 | 10 | 70 | 155 | 10850 | 2170 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 10850 |  | 10850 |  |  |  | 8680 |  |  | 8680 | 2170 | 10850 | 10850
12 | 10 | 70 | 155 | 10850 | 2170 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 10850 |  | 10850 |  |  |  | 8680 |  |  | 8680 | 2170 | 10850 | 10850
13 | 10 | 70 | 155 | 10850 | 2170 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 10850 |  | 10850 |  |  |  | 8680 |  |  | 8680 | 2170 | 10850 | 10850
14 | 10 | 70 | 155 | 10850 | 2170 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 10850 |  | 10850 |  |  |  | 8680 |  |  | 8680 | 2170 | 10850 | 10850
15 | 10 | 60 | 145 | 8700 | 1740 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 12 | [8 empty] | 8700 |  | 8700 |  |  |  | 6960 |  |  | 6960 | 1740 | 8700 | 8700
16 | 10 | 60 | 145 | 8700 | 870 | 8 | Residential Hospitality Suites Flex 2 bed/2bath - sleep 6 | [9 empty] | 8700 | 8700 |  |  |  |  | 6960 |  | 6960 | 1740 | 8700 | 8700
17 | 10 | 60 | 145 | 8700 | 1740 | 4 | Residential Hospitality Suites Flex 3-4 bed/2bath - sleep 10 | [9 empty] | 8700 | 8700 |  |  |  |  | 6960 |  | 6960 | 1740 | 8700 | 8700
18 | 10 | 60 | 145 | 8700 | 1740 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 10 | [8 empty] | 8700 |  | 8700 |  |  |  | 6960 |  |  | 6960 | 1740 | 8700 | 8700
19 | 10 | 60 | 145 | 8700 | 1740 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 10 | [8 empty] | 8700 |  | 8700 |  |  |  | 6960 |  |  | 6960 | 1740 | 8700 | 8700
20 | 10 | 60 | 145 | 8700 | 1740 | 4 | Residential Condos Flex 3-4 bed/2bath - sleep 10 | [8 empty] | 8700 |  | 8700 |  |  |  | 6960 |  |  | 6960 | 1740 | 8700 | 8700
21 | 10 | 60 | 145 | 8700 | 2320 | 3 | Residential Condos Flex 3-4 bed/2bath - sleep 10 | [8 empty] | 8700 |  | 8700 |  |  |  | 6960 |  |  | 6960 | 1740 | 8700 | 8700
22 | 10 | 60 | 145 | 8700 | 3480 | 2 | Residential Condos Flex 3-4 bed/2bath - sleep 10 | [8 empty] | 8700 |  | 8700 |  |  |  | 6960 |  |  | 6960 | 1740 | 8700 | 8700
23 | 13.25 | 60 | 145 | 8700 | 3480 | 2 | Residential Penthouse | [8 empty] | 8700 |  | 8700 |  |  |  | 6960 |  |  | 6960 | 1740 | 8700 | 8700
roof top |  | 60 | 145 | 8700 | 6960 | 1 | Pool/Dead Sea Float Mini-Spa/Restaurant | [5 empty] | 6960 | 1740 |  |  |  | 8700 |  | 1392 |  |  |  | 5568 | 6960 | 1740 | 8700
Total | 240 |  |  | 260775 |  | 75 | GSF | 1640.625 | 3281.25 | 15750 | 47250 | 2000 | 6960 | 1740 | 8203.125 | 147700 | 26250 | 260775 | 19031.25 | 1740 | 8203.125 | 147700 | 26250 | 57850.625 | 260775 | 52155 | 260775 | 238950
[7 empty] | %GSF | 0.6291% | 1.258% | 6.04% | 18.12% | 0.7669% | 2.669% | 0.6672% | 3.146% | 56.64% | 10.07% | 100% | 7.298% | 0.6672% | 3.146% | 56.64% | 10.07% | 22.18% | 100% | 20% | 100% | 91.63%
[7 empty] | NSF | 1312.5 | 2625 | 12600 | 37800 | 1600 | 5568 | 1392 | 6562.5 | 118160 | 21000 | 208620 | 15225 | 1392 | 6562.5 | 118160 | 21000 | 46280.5 | 208620 | 52155 |  | 191160
[7 empty] | %NSF | 0.6291% | 1.258% | 6.04% | 18.12% | 0.7669% | 2.669% | 0.6672% | 3.146% | 56.64% | 10.07% | 100% | 7.298% | 0.6672% | 3.146% | 56.64% | 10.07% | 22.18% | 100% |  |  | 91.63%
[7 empty] | QTY of Units | 1 | 1 | 1 | 153 | 1 | 1 | 1 | 2 | 55 | 20
[8 empty] | Square Ft. Breakdown | [5 empty] | Sales by Square Ft. Breakdown
[7 empty] | Saleable / Non Saleable | GSF | %GSF | NSF | %NSF | %NSF/GSF | Avg. NSF /Unit | $SF | $Unit | Total $
[6 empty] | 1 | Synagogue - Mikvah Saleable @ Cost | 19031.25 | 7.298% | 15225 | 7.298% | 5.838% | 15225 | 500 | 7612500 | 7612500
[6 empty] | 1 | Saleable Restaurant | 1740 | 0.6672% | 1392 | 0.6672% | 0.5338% | 1392 | 1300 | 1809600 | 1809600
[6 empty] | 2 | Saleable Commercial | 8203.125 | 3.146% | 6562.5 | 3.146% | 2.517% | 3281.25 | 1200 | 3937500 | 7875000
[6 empty] | 55 | Saleable Residential | 147700 | 56.64% | 118160 | 56.64% | 45.31% | 2148.3636 | 1200 | 2578036.364 | 141792000
[6 empty] | 20 | Saleable Residential Hospitality | 26250 | 10.07% | 21000 | 10.07% | 8.053% | 1050 | 1350 | 1417500 | 28350000
[7 empty] | Non-Saleable Common areas | 57850.625 | 22.18% | 46280.5 | 22.18% | 17.75%
[6 empty] | 24 | Total Floor Usable | 260775 | 100% | 208620 | 100% | 80% | 8692.5 | SF | Total Revenue | 187439100
[7 empty] | Total Saleable | 202924.375 | 77.82% | 162339.5 | 77.82% | 62.25% |  | 162339.5 | $NSF Saleable | 1154.6118
[7 empty] | Total Non Saleable | 57850.625 | 22.18% | 46280.5 | 22.18% | 17.75% |  | 202924.375 | $GSF Saleable | 923.6894
[8 empty] | Square Ft Strutural | [5 empty] | 208620 | $NSF Total | 898.4714
[7 empty] | Total Structural | 52155 | 20% |  |  | 20% |  | 260775 | $GSF Total | 718.7771
[7 empty] | Total Non-Structural | 208620 | 80%
Floor Plate Sizes and use
[8 empty] | GSF/FLR | T-GSF | Qty of Floors | T-GSF
[7 empty] | Floor 1 - Lobby / 2-Commercial / Mikvah | 13125 |  | 1 | 13125
[7 empty] | Floor 2-5 (2=Synagogue, 3-5=Parking) | 15750 | 63000 | 4 | 63000
[7 empty] | Floor 6-14 Residential / Floor 6-Residential & Gym | 10850 | 97650 | 9 | 97650
[7 empty] | Floor 15-23-Residential | 8700 | 78300 | 9 | 78300
[7 empty] | Rooftop-Pool | 8700 |  | 1 | 8700
[9 empty] | 238950 |  | 260775
[7 empty] | Hard Costs (Direct Construction) | 59500000 | 77.27% | Core building expenses, reduced via in-kind materials/labor. |  |  |  |  | Cost by Square Ft. Breakdown |  |  | GSF | NSF | Saleable GSF | Saleable NSF
[7 empty] | Site Preparation & Foundation | 12000000 | 15.58% | Excavation, piling, utilities connection; waterfront site adds resilience costs. |  |  |  |  | Hard Cost | 59500000 | 65.38% | 228.166 | 285.2076 | 293.2127 | 366.5159
[7 empty] | Structure & Exterior (Frame, Roof, Envelope) | 15000000 | 19.48% | Concrete/steel framing for 24 stories, facade, windows; ~$57/GSF. |  |  |  |  | Soft Cost | 17500000 | 19.23% | 67.1077 | 83.8846 | 86.239 | 107.7988
[7 empty] | Interiors & Finishes | 15000000 | 19.48% | Unit build-outs, common areas, amenities (pool, gym); luxury specs. |  |  |  |  | Total | 77000000 | 84.62% | 295.2737 | 369.0921 | 379.4517 | 474.3146
[7 empty] | Mechanical, Electrical, Plumbing (MEP) | 14500000 | 18.83% | HVAC, elevators, fire systems; energy-efficient for fee reductions. |  |  |  |  | Land | 14000000 | 15.38% | 53.6861 | 67.1077 | 68.9912 | 86.239
[7 empty] | Landscaping & Exterior Amenities | 3000000 | 3.896% | Rooftop pool/spa, parking garage finishes. |  |  |  |  | Land+Hard+Soft | 91000000 | 100% | 348.9598 | 436.1998 | 448.4429 | 560.5537
[7 empty] | Soft Costs (Indirect/Supporting) | 17500000 | 22.73% | Planning, fees, overhead; expedited processes lower some.
[7 empty] | Design & Engineering (Architect, Engineer) | 4000000 | 5.195% | Plans, RFQ responses; in-kind from super team.
[7 empty] | Permitting & Fees | 3000000 | 3.896% | Reduced 15% via amenities; site plan review, impact fees.
[7 empty] | Marketing & Sales | 3000000 | 3.896% | Pre-sales, broker fees; targets Jewish/luxury buyers.
[7 empty] | Legal & Insurance | 3000000 | 3.896% | Contracts, liability; partner contributions.
[7 empty] | Project Management & Overhead | 1500000 | 1.948% | GP oversight, AI tools, owners' rep.
[7 empty] | Contingencies & Miscellaneous | 3000000 | 3.896% | 8% buffer for overruns, inflation; includes potential bridge if agreed.
[7 empty] | Total | 77000000 | 100% | Aligned with $350-500/GSF Miami-Dade averages, post-20% in-kind savings.

## zoning-design guidelines
General envelope limitations
Zonning T6-24 form base code | Width | Mezzanine | Lentgh | Total SqFt | Acreage | Residential Units per Acre | Residential Units allowed | 90% max coverage |  | 10% Free Air Space space | Work Force Housing, 80% of Income | Common Areas
Lot Size | 100 | 50% of Ground floor | 200 | 20000 | 45.91% | 150 | 68.8705 | 18000 |  | 2000 | 5% | 15% or Less
PARKING REQUIREMENTS | [9 empty] | INTENSITY
Parking Residential | Synagogue Parking | Commercial Parking | Hotel Parking | Total Parking spaces required | Parking Space measures | Driving lanes | Day Care Parking |  |  | Hotel Density / Intensity
1 per unit + Visitors 1 per 10 units = 76 | 1 space for every 5 chairs = 20 | 1k sf = 3 spaces | 2 rooms = 1 space + 1 space for every 15 rooms |  | 9' x 15' | 12' | 2 spaces per 1k sf |  |  | no restrictions
| 120 spaces | 10k sqft
76 | 24 | 30 |  | 130
General Restrictions
Max building envelope = 13 x Lot size (20,000) = 260kSF (floor lot ratio)
There is no Density restriction for Lodging
Loading zone = 420 sf, 12x35 ft w/clearance 15th ft
Ground floor hieght minimum 20'
Ground floor has additonal 15 ft. self imposed setback for the access and exit of vehicles
BulkHead for Elevator and Stairs do not count as structure on Roof - does not decrease the Hieght Allowance of 240'
Lounge Area with Small Kitchen area does not count as structure - does not decrease the Hieght Allowance of 240'
Setbacks / Floor plate sf
SETBACKS | 1 floor | 2-5 floor | 6-14 Floor | 15-23 | Roof Top | Totals
Side 1 - West | 15 | 0 | 10 | 15 | 15
Side 2 - East | 10 | 10 | 20 | 25 | 25
Front - North | 20 | 20 | 30 | 35 | 35
Rear - South | 5 | 5 | 15 | 20 | 20
Floor Count | 1 | 4 | 9 | 9 | 1 | 24
Set Back SF | 7500 | 4500 | 10500 | 13500 | 13500
Floor Plate Measurent | 75 x 175 | 90 x 175 | 70 x 155 | 60 x 145 | 60 x 145
Floor Plate SF | 13125 | 15750 | 10850 | 8700 | 8700
Total Building SF | 13125 | 63000 | 97650 | 78300 | 8700 | 260775
Floors | West (Side1) ft | East (Side2) ft | North (Front) ft | South (Rear) ft | Setback SF (as given) | Floor Plate Measurement | Floor Plate SF | QTY of Floors | Total SF of floor type | Notes
1 | 15 | 10 | 20 | 5 | 7500 | 75 x 175 | 13125 | 1 | 13125 | Width=100-15-10=75, Length=200-20-5=175; 15' west is setback for vehicle access not for zoning required setback
2025-02-05 | 0 | 10 | 20 | 5 | 4500 | 90 x 175 | 15750 | 4 | 63000 | Width=100-0-10=90; Per floor, total 4 floors, 63000 SF.
2025-06-14 | 10 | 20 | 30 | 15 | 10500 | 70 x 155 | 10850 | 9 | 97650 | Width=100-10-20=70, Length=200-30-15=155; 9 floors, 97650 SF.
15-23 | 15 | 25 | 35 | 20 | 13500 | 60 x 145 | 8700 | 9 | 78300 | Width=100-15-25=60, Length=200-35-20=145; 9 floors, 78300 SF.
Roof | 15 | 25 | 35 | 20 | 13500 | 60 x 145 | 8700 | 1 | 8700 | Same as 15-23; 1 "floor".
Total | - | - | - | - |  | - |  |  | 260775

## Comments
Analysis of Square Footage Ratios vs. Industry Standards
Based on research, here's an evaluation of the project's ratios (from spreadsheet: GSF 260,775; Total NSF/Usable 208,620 (80%); Salable NSF 160,627 (62% of GSF, 77% of NSF); Non-Salable/Common Areas 47,993 (23% of NSF, 18% of GSF); Structural (implied as GSF - NSF = 52,155 or 20% of GSF). Industry standards for high-rise condominiums (typically 20-50 stories) are drawn from sources like BOMA standards, architectural guidelines, and real estate metrics: Efficiency (salable/useful to gross) often 70-85%; common areas 15-30%; structural/loss factors 10-20%.
GSF to NSF (Efficiency Ratio: 80%): Inline—Standard for condos is 75-85% (NASF/GSF), accounting for walls, shafts. High-rises often hit 80% with efficient designs.
Salable NSF to Non-Salable (77% Salable / 23% Common Areas): Inline—Common areas (lobbies, parking, amenities) typically 20-30% of usable space; luxury projects with pools/gyms lean toward 25%.
Salable NSF to GSF (62%): Slightly low—Industry average 70-80% for condos (net salable to gross); lower if high structural needs (e.g., waterfront resilience). Highlight: This may indicate conservative planning or excess common/structural space; optimize to 70% for better revenue.
Structural to GSF (20%): Inline—Typical loss factor (walls, columns) 15-25%; efficient for concrete high-rises.
Overall, ratios are mostly standard, but salable-to-GSF at 62% is a potential outlier—could be improved by minimizing non-salables.
https://leolaconstruction.com/contact-us/ | 11849 US HWY 41 S, GIBSONTON, FL 33534 | shell construction
https://www.admerconstruction.com/contact-us/ | 5775 Waterford District Dr # 100, Miami, FL 33126 | shell construction

## Introduction-Overview
Introduction to the New Project Model: "Partners Not Paychecks"
The NeVo Tower introduces an innovative cooperative development model called "The Miami Makers - Co-Developers Partners Not Paychecks," designed to revolutionize real estate projects by minimizing cash investments, reducing risks, and fostering equitable collaboration among professionals. In this system, partners such as architects, engineers, contractors, lawyers, suppliers, and even accountants contribute expertise, services, or materials in-kind rather than upfront capital. These contributions are valued at market rates and treated as investments, earning partners a pro-rata share of the huge projected profits, plus a time-weighted 8% annualized preferred return to reward early participation and higher risk exposure.
This approach eliminates traditional financing barriers, cuts construction costs by up to 20% per square foot, and accelerates timelines by avoiding lender delays and interest payments. Profit-sharing is transparent and milestone-driven: Distributions begin quarterly from Month 18, triggered by sales exceeding 20% increments of salable area (e.g., 32,125 NSF per cutoff) or when available cash surpasses $5M, allowing payouts before full project completion. All partners, including cash contributors have access to perks like 20% unit discounts and tax depreciation. All Partners including the Land Partner ($14M land), are treated equally based on contribution value and timing, with AI-powered tools providing real-time updates on costs, progress, and sales.
A key advantage is the inherently lower risk of financial loan stress, as the model operates without loans or external debt, removing pressures from interest accrual or lender demands. This debt-free structure also enables a significant sales advantage: Offering self-financing options to regular buyers, where partners can opt to fund these mortgages based on their shares of the partnership value. For participating partners, this extends their return horizon while reducing their tax bill through interest income treatment and potential deductions; the issued mortgages can serve as collateral for other financial needs, enhancing liquidity without compromising project equity. Rates will be very competitive, with incentives like spiffs, easier or faster closings, facilitated through a dedicated private lender partner who shares in the profits.
Without the rush or fear of financial loan stress, the model allows strategic timing to capitalize on market conditions, such as waiting for interest rates to decline or real estate prices to rise—maximizing revenue without forced sales. Should small bridge financing be required for interim needs and agreed to by Partners, the project's strong equity position (backed by in-kind assets and no existing debt) provides a huge negotiating advantage for favorable rates and terms. Partners can further benefit by electing to retain all or part of the hospitality suites for operation as short-term rentals (STR), generating perpetual residual income, while enjoying reduced tax liabilities through depreciation and operational deductions. Any profits from the project can be rolled into future developments via 1031 exchanges, deferring capital gains taxes and enabling seamless scaling.
Additional Advantages of This Model
Faster Decision-Making and Execution: By assembling a super team of top professionals contributing in-kind, the project bypasses bureaucratic financing hurdles, potentially shortening overall development timelines by 6-12 months compared to traditional models, as decisions are made collaboratively without lender vetoes.
Scalability and Network Effects: Successful partnerships build a reusable ecosystem for future projects, reducing onboarding costs and fostering long-term alliances that lower risks in subsequent ventures.
Enhanced Resilience to Economic Volatility: The cushion from cost savings and flexible timing mitigates downturns; for instance, idle cash can be invested in low-risk US short-term Treasury bonds to earn yields while awaiting optimal market conditions.
Project Overview
The NeVo Tower project is a 24-story (23 floors + rooftop) luxury mixed-use condominium at 1580 79th St Causeway, North Bay Village, FL 33141. It features 55 condominiums (118,160 sf, ~2,148 sf/unit, priced at $1,400/sf = $165M), 20 hospitality suites (20,600 sf, ~1,030 sf/unit, priced at $1,600/sf = $33M), Synagogue / Mikvah (15,000 sf $10M ), Rooftop pool/restaurant and 2 Retail units in lobby area. Total GSF: 260,775 sf; Net Saleable NSF: 160,627 sf; Total revenue $200M+. The project is currently in the middle of site planning, with concept development, due diligence on site potential, and payment for city site plan review already completed. Construction is slated to begin in Q3 2026. Sales commence in Month 1 for cash partners (20 buyers contributing $34M at preferred rates with 20% unit discounts and tax benefits like depreciation) and after permits are issued for general sales (usually 6-12 months after site plan approval). As of July 18, 2025, the project aligns with North Bay Village's ongoing transformation.
Total Costs: $91M, Reduced via in-kind contributions; no debt. The development leverages a self-financing model that eliminates traditional lender approvals and interest risks, providing a $500/NSF cushion against market downturns. Permitting and impact fees are reduced by 15% due to community-focused amenities like the synagogue and mikvah. Projected Profit: Huge, Distributed equitably with 8% preferred return on contributions. Timeline: Q3 2026 start; Q3 2029 complete (placeholder), Sales milestones trigger quarterly payouts from Month 18; fast-track permitting could accelerate pre-construction. | 10500000
Summary of the Nevo Tower Project
Project Name: Nevo Tower
Address: 1580 79th St Causeway, North Bay Village, FL 33141
Zoning: T6-24 (permits hospitality suites and short-term rentals)
Scope: A 24-story mixed-use tower featuring 55 condominiums, 20 hospitality suites, a synagogue, a mikvah, and a rooftop pool and restaurant, designed to offer luxury living with uninterrupted views of Biscayne Bay, Miami, Miami Beach, and South Beach. The project targets Miami’s Jewish community and high-end buyers seeking premium residences and investment opportunities through short-term rental suites. As of July 18, 2025, aligns with NBV's transformation (e.g., Related/Macklowe 43-story towers).
Physical Specifications:
Total Gross Square Footage: 260,775 sf
Net Saleable Square Footage: 160,627 sf
Condominiums: 118,160 sf (55 units, ~2,148 sf/unit, priced at $1,400/sf = $165M)
Hospitality Suites: 20,600 sf (20 units, ~1,030 sf/unit, priced at $1,600/sf = $33M)
Additional Amenities:
Synagogue: ~5,000–10,000 sf with separate seating, designed for community use.
Mikvah: ~1,000–2,000 sf, halachic-compliant.
Rooftop Pool and Restaurant: Enhancing luxury appeal and revenue potential.
Timeline:
0–6 Months: Pre-site plan approval.
6–18 Months: Permitting approval with North Bay Village/Miami-Dade.
18–36 Months: Demolition and construction, targeting completion between Q3 2029 and Q3 2030.
Construction and Design:
Designed by a leading architect to meet Miami-Dade County standards, ensuring compliance with high-rise regulations.
Constructed by an experienced high-rise contractor, with oversight by the owner’s representative to maintain quality and efficiency.
Features modern, high-end finishes tailored to luxury buyers, with suites zoned for short-term rentals to maximize investment returns.
Marketing and Appeal:
Marketed in-house to Miami’s Jewish community and luxury buyers, emphasizing panoramic views, proximity to Miami’s urban core, and the unique combination of residential, hospitality, and community-focused amenities.
Pre-sale contracts comply with Chapter 718, Florida Statutes, with funds held in escrow to ensure buyer confidence.
Operational Notes:
The project leverages the T6-24 zoning to offer flexible use of hospitality suites for short-term rentals, appealing to investors.
The synagogue and mikvah enhance cultural resonance, positioning Nevo Tower as a community hub.
The rooftop pool and restaurant add a premium lifestyle component, differentiating the project in the competitive Miami market.
These advantages highlight the comprehensive benefits of participating in the "Partners Not Paychecks" model, emphasizing collaboration, shared success, and innovative practices.
Involvement in a High-Profile Project: Participation in a landmark development project that offers significant visibility and prestige.
Equitable Profit Sharing: Partners receive a share of the project's profits, providing an additional revenue stream beyond standard contracts or fees.
Long-Term Partnership Potential: The opportunity to establish a long-term relationship with potential involvement in future projects.
Networking Opportunities: Collaborate with top professionals across various fields, enhancing your network and opening doors to new business opportunities.
Control Your Own Destiny: Partners have a direct stake in the project's success, allowing them to influence outcomes and benefit from collective achievements.
Innovative Model Participation: Being part of a pioneering development approach that could set new industry standards, enhancing your reputation as forward-thinking and innovative.
Cost Efficiency: Reduced costs through collaborative efforts and shared resources.
Accelerated Timelines: Faster project completion due to streamlined processes and collaborative decision-making.
Reduced Financial Risk: Lower financial risk through shared responsibilities and resources.
Enhanced Profitability: Increased profitability through efficient resource allocation and shared success.
Flexible Financing Options: Access to flexible financing solutions tailored to the project's needs.
Improved Decision-Making: Better decision-making through collective input and shared expertise.
Strategic Market Adaptation: Ability to adapt to market conditions strategically, maximizing revenue without forced sales.
Increased Resilience: Enhanced resilience to economic volatility and market fluctuations.
Optimized Resource Utilization: Efficient use of resources, reducing waste and improving project outcomes.
Streamlined Processes: Simplified and more efficient project management processes.
Sustainable Growth: Opportunities for sustainable growth and long-term success.
Community-Centric Development: Focus on community benefits and enhancements, improving the project's social impact.
More Secured Payments: Greater security in receiving payments through structured and agreed-upon financial arrangements.
Tax Benefits: Potential tax advantages from the profit-sharing model and the structure of payments.
Transparent and Translucent Payment: Payments are made in a transparent manner, ensuring clarity and trust among all partners.
Guaranteed Customer with Agreed Delivery Dates: Assurance of business with pre-agreed delivery schedules that benefit both the supplier and the development.
Moving Supplies Efficiently: Ability to manage and move supplies as needed, optimizing logistics and inventory management for the benefit of the project timeline and budget.
These advantages highlight the comprehensive benefits of participating in the "Partners Not Paychecks" model, emphasizing collaboration, shared success, and innovative practices.
names similar to the "Partners Not Paychecks" model:
Alliance for Advancement
Alliance for Assets
Collaborate to Capitalize
Collaborate to Compensate
Collaboration for Capital
Collaborative Capital Coalition
Collaborative Compensation Circle
Collective Capital Ventures
Collective Compensation Club
Contribution Collective
Cooperative Capital Collective
Equity Collaborative
Equity Exchange Enterprise
Equity Over Earnings
Equity Over Invoices
Expertise Exchange Equity
In-Kind Investors
In-Kind to Income
Joint Venture Junction
Mutual Growth Matrix
No Cash, All Equity
Partners in Profit
Partners in Progress
Partners Not Paychecks
Profit Partners Program
Profit Partnership Program
Profits for Partnership
Prosperity Through Partnership
Return on Resources
Shared Stake Society
Shared Stake Synergy
Shared Success Syndicate
Shares Over Checks
Skills to Shares
Stakeholders Not Salaries
Sweat Equity Syndicate
Synergy Stakeholders
Trade Talent for Treasure
United Ventures Union
Unity for Profitability
Unity for Upside
Value for Victory
Value Vault Ventures

## Pitch-Email-Rap-phases
Elevator Pitch for NeVo Tower Money PartnersPicture investing in NeVo Tower, a 23-story luxury condominium in North Bay Village, FL, set to generate $186M in revenue. As a money partner, your cash investment fuels a groundbreaking project, earning you a share of potential profits exceeding $65M, distributed equitably as sales milestones are hit, starting around Month 18. Contribute to our $34M cash pool and enjoy exclusive perks, like buying units at preferential partner rates. Our model cuts costs by 20% per square foot, skips financing delays, and uses AI for transparent updates. With Tykun Luxury Ltd.’s $14M land contribution and a Q3 2026 start, you’ll gain high returns, tax benefits, and priority for future projects. Ready to profit as a partner? Let’s talk.Notes on the Pitch$186M Revenue: Updated to reflect the new revenue figure, ensuring accuracy per your request.
Profit-Sharing: Phrased as “a share of potential profits exceeding $65M, distributed equitably as sales milestones are hit, starting around Month 18” to be less precise and less promising, while still highlighting the attractive profit pool ($65M+).
Preferential Pricing Perk: Added “enjoy exclusive perks, like buying units at preferential partner rates” to emphasize the unique benefit for money partners, aligning with Section 2.7 of the Partnership Agreement (option to purchase units at a discount).
Money Partner Focus: Tailored to cash investors by referencing the $34M cash pool (from prior discussions, where 20 cash partners contribute starting Month 1) and emphasizing financial returns, tax benefits, and low risk through the cooperative model.
Partners Ethos: Highlighted the collaborative model with phrases like “profit as a partner” and “equitably,” tying to the “Partners Not Paychecks” concept without directly quoting it.
Additional ConsiderationsThe pitch assumes money partners contribute to the $34M cash pool, as discussed previously, with profit distributions based on an Average Daily Balance qualifier starting in Month 18. If you want to specify a minimum investment amount or more details about the preferential pricing (e.g., percentage discount), I can refine the pitch.
The pitch is broad to appeal to high-net-worth individuals or investment groups. If targeting a specific type of money partner (e.g., real estate funds, private investors), I can adjust the tone or details.
The 23-story figure and 260,775 sq. ft. gross area align with prior discussions, correcting the 24-story mention in some memories to ensure consistency with the Partnership Agreement.
Email Introduction: NeVo Tower Partnership SystemSubject: Join the NeVo Tower Partnership – Shape Miami’s Skyline as a Partner, Not a PaycheckDear [Recipient Name],We’re thrilled to introduce the NeVo Tower, a 23-story luxury condominium in North Bay Village, FL, set to redefine real estate development with a projected $186M in revenue. At Tykun Luxury Ltd., we’re launching an innovative partnership system that transforms how professionals and investors collaborate on high-impact projects.Our Partnership System: Unlike traditional models, our “Partners Not Paychecks” approach invites professionals—contractors, architects, engineers, MEP subcontractors, and material suppliers—to contribute expertise or materials, and cash partners to invest funds, with no upfront financial barriers for professionals. In return, you’ll share in significant profits, potentially exceeding $65M, distributed equitably based on your contributions as sales milestones are reached, starting around Month 18. Cash partners also enjoy exclusive perks, like purchasing units at preferential rates.Why Join?Cost Efficiency: Our streamlined model cuts costs by 20% per square foot, bypassing lender delays for a Q3 2026 start and Q3 2029 completion.
Transparency: AI-powered tools provide real-time updates on project progress, costs, and sales.
Benefits: Gain visibility, tax advantages, priority for future projects, and, for cash partners, discounted unit pricing.
Low Risk: Professionals contribute services/materials, not cash; cash partners leverage Tykun’s $14M unencumbered land contribution.
NeVo Tower is more than a project—it’s a chance to build a Miami landmark as a true partner. With 55 condominiums, 20 hospitality suites, a rooftop restaurant, synagogue, and mikvah, this development targets luxury buyers and the local community.Next Steps: Reply to schedule a call with our team to discuss how your expertise or investment can shape NeVo Tower’s success. We’ll share detailed financials, timelines, and partnership terms.Best regards,
Eli
Managing Member, Tykun Luxury Ltd.
305-905-5068 ¦ tykunluxury@gmail.com
1580 79th Street JFK Causeway, North Bay Village, FL 33124 Text Message Introduction: NeVo Tower Partnership SystemJoin NeVo Tower, a $186M luxury condo project in Miami! Our “Partners Not Paychecks” system lets professionals contribute expertise/materials and cash partners invest funds to share in potential $65M+ profits, starting ~Month 18. Enjoy cost savings, AI transparency, tax benefits, and, for cash partners, unit discounts. Reply to learn how to partner on this Q3 2026 landmark! Eli, 305-905-5068.
20-Second Rap for NeVo Tower PartnershipYo, NeVo Tower, Miami’s the vibe,
$186M, where dreams come alive!
Pros bring skills, cash folks provide,
Partners, not paychecks, we roll side by side!
Big profits shared fair, when sales hit the stride,
Month 18 payouts, we’re ridin’ the tide.
Cut costs, AI tracks, units priced sweet,
Join Tykun’s vision, let’s own the street!
20-Second Rap for NeVo Tower PartnershipYo, NeVo Tower, Miami’s new crown,
$186M, we’re shakin’ the town!
Pros drop skills, cash partners bring heat,
No paychecks here, just partners that meet!
Profits roll big, split fair when sales soar,
Month 18 cash, openin’ the door.
Save big, AI tracks, units priced tight,
Tykun’s the spark—let’s ignite the night!
Phase Categories
Pre-Development: Project Initiation, Feasibility Analysis, Legal and Financial Setup, Permitting and Approvals
Design and Planning: Architectural Design, Structural Engineering, Sustainability and Innovation
Pre-Construction: Project Management, Marketing and Sales Preparation, Insurance and Risk Management
Construction: Site Preparation and Foundation, Structural Construction, Interiors and Finishes, MEP Installation, Sales and Marketing Execution
Post-Construction: Sales Completion, Financial and Legal Closeout, Operational Transition
Buzzwords for the New Development Model
Innovative Cooperation
Equitable Collaboration
In-Kind Contributions
Profit-Sharing Partnerships
Risk Mitigation
Transparent Profit Distribution
Milestone-Driven Distributions
AI-Powered Real-Time Updates
Self-Financing Model
Debt-Free Structure
Strategic Market Timing
Scalable Partnerships
Collaborative Decision-Making
Efficient Resource Allocation
Sustainable Development
Buzzwords for the Advantages of Using This Model
Cost Efficiency
Accelerated Timelines
Reduced Financial Risk
Enhanced Profitability
Flexible Financing Options
Equitable Profit Sharing
Real-Time Cost Tracking
Improved Decision-Making
Strategic Market Adaptation
Long-Term Alliances
Increased Resilience
Optimized Resource Utilization
Streamlined Processes
Sustainable Growth
Community-Centric Development
Phrases for the New Development Model
Collaborate to Elevate
Build Together, Prosper Together
Unity in Development
Shared Success, Shared Growth
Innovate as One
Partners in Progress
Collective Vision, Collective Victory
Strength in Synergy
Grow Together, Build Forever
United We Build
Partnerships Over Profits
Together We Rise
Collaborative Construction
Shared Dreams, Shared Schemes
Harmony in Building
Together We Thrive
Shared Vision, Shared Victory
Building Bonds, Building Futures
United Efforts, Unlimited Success
Collaborative Foundations
Partners in Innovation
Collective Strength, Collective Success
Building Dreams Together
Shared Goals, Shared Growth
Unity in Construction
Partners for Progress
Together We Achieve
Shared Ambitions, Shared Achievements
Collaborative Growth
Innovate Together, Succeed Together
Telephone Pitch for Potential Attorney Partner
You: Hello [Attorney's Name],
I hope you're doing well. I'm calling to introduce an exciting opportunity for [Attorney's Firm Name] to be a part of a pioneering development project here in North Bay Village, Florida—the NeVo Tower.
The NeVo Tower is a 24-story luxury mixed-use condominium that is set to redefine collaborative development with our innovative "Partners Not Paychecks" model. This approach emphasizes shared success and equitable profit distribution among all partners, including legal experts like yourself.
We are seeking a legal partner to manage all legal aspects of the project, from contract drafting and compliance to risk management and dispute resolution. Your firm's expertise in real estate law would be invaluable to us, ensuring the project's legal integrity and success.
Here are some key benefits for your firm:
High-Profile Project Involvement: The NeVo Tower is set to become a landmark in Miami, offering significant visibility and prestige for your firm.
Equitable Profit Sharing: Beyond standard legal fees, your firm will receive a share of the project's profits, providing an additional revenue stream.
Long-Term Partnership Potential: This project could lay the foundation for a lasting relationship, with potential involvement in future developments using our innovative model.
Networking Opportunities: Collaborate with top professionals across various fields, enhancing your firm's network and opening doors to new business opportunities.
Innovative Model Participation: Be part of a pioneering development approach that could set new industry standards, enhancing your firm's reputation as forward-thinking and innovative.
We would love to schedule a meeting to discuss this opportunity further and explore how we can work together to make the NeVo Tower a resounding success.
Thank you for considering this opportunity. I look forward to the possibility of working together.
Best regards,
[Your Name]
[Your Position]
[Your Contact Information]
Email Pitch for Potential Attorney Partner
Subject: Exciting Legal Partnership Opportunity with NeVo Tower Development
Dear [Attorney's Name],
I hope this message finds you well. I am writing to introduce an exciting opportunity for [Attorney's Firm Name] to participate in a groundbreaking development project in North Bay Village, Florida—the NeVo Tower.
The NeVo Tower is a 24-story luxury mixed-use condominium that introduces an innovative cooperative development model called "Partners Not Paychecks." This model emphasizes collaboration, shared success, and equitable profit distribution among all partners involved.
We are looking for a legal partner to oversee all legal aspects of this development, from contract drafting and compliance to risk management and dispute resolution. Given your firm's stellar reputation and expertise in real estate law, we believe you would be an invaluable addition to our team.
Here are some key benefits for your firm:
Involvement in a High-Profile Project: The NeVo Tower is set to be a landmark development in Miami, offering significant visibility and prestige for your firm.
Equitable Profit Sharing: As a partner, your firm will not only receive standard legal fees but also a share of the project's profits, providing an additional revenue stream.
Long-Term Partnership Potential: This project could be the beginning of a long-term relationship, with potential involvement in future developments leveraging our innovative model.
Networking Opportunities: Collaborating with top professionals across various fields, enhancing your firm's network and opening doors to new business opportunities.
Innovative Model Participation: Being part of a pioneering development approach that could set new standards in the industry, enhancing your firm's reputation as forward-thinking and innovative.
We believe that your expertise will be crucial in navigating the legal landscape of this project and ensuring its success. We would love to schedule a meeting to discuss this opportunity further and explore how we can work together to make the NeVo Tower a resounding success.
Thank you for considering this opportunity. I look forward to the possibility of working together.
Best regards,
[Your Name]
[Your Position]
[Your Contact Information]
Text Pitch for Suppliers
You: Hi [Supplier's Name],
I'm reaching out to discuss an exciting opportunity for [Supplier's Company Name] to partner with us on the NeVo Tower project, a groundbreaking 24-story luxury mixed-use condominium in North Bay Village, FL.
The NeVo Tower is pioneering a new development model called "Partners Not Paychecks," which emphasizes collaboration and shared success. We are looking for material suppliers to join us as partners, contributing to and benefiting from the project's success.
Here are some key benefits for your company:
High-Profile Project Involvement: The NeVo Tower is set to be a landmark in Miami, offering significant visibility and prestige.
Equitable Profit Sharing: As a partner, your company will receive a share of the project's profits, providing an additional revenue stream beyond standard supply contracts.
Long-Term Partnership Potential: This project could be the start of a long-term relationship with potential involvement in future developments.
Networking Opportunities: Collaborate with top professionals across various fields, enhancing your company's network and opening doors to new business opportunities.
Control Your Own Destiny: As a partner, you have a direct stake in the project's success, allowing you to influence outcomes and benefit from the collective achievements.
Innovative Model Participation: Be part of a pioneering development approach that could set new industry standards, enhancing your company's reputation as forward-thinking and innovative.
We would love to schedule a meeting to discuss this opportunity further. Thank you for considering this opportunity.
Best regards,
[Your Name]
[Your Position]
[Your Contact Information]
Email Pitch for Suppliers
Subject: Exciting Partnership Opportunity with NeVo Tower Development
Dear [Supplier's Name],
I hope this message finds you well. I am writing to introduce an exciting opportunity for [Supplier's Company Name] to participate in the NeVo Tower project, a pioneering 24-story luxury mixed-use condominium in North Bay Village, FL.
The NeVo Tower introduces an innovative cooperative development model called "Partners Not Paychecks," emphasizing collaboration and shared success. We are seeking material suppliers to join us as partners, contributing to and benefiting from the project's success.
Here are some key benefits for your company:
Involvement in a High-Profile Project: The NeVo Tower is set to be a landmark development in Miami, offering significant visibility and prestige for your company.
Equitable Profit Sharing: As a partner, your company will receive a share of the project's profits, providing an additional revenue stream beyond standard supply contracts.
Long-Term Partnership Potential: This project could be the beginning of a long-term relationship, with potential involvement in future developments leveraging our innovative model.
Networking Opportunities: Collaborate with top professionals across various fields, enhancing your company's network and opening doors to new business opportunities.
Control Your Own Destiny: As a partner, you have a direct stake in the project's success, allowing you to influence outcomes and benefit from the collective achievements.
Innovative Model Participation: Be part of a pioneering development approach that could set new industry standards, enhancing your company's reputation as forward-thinking and innovative.
We believe your expertise and materials will be crucial in ensuring the success of this project. We would love to schedule a meeting to discuss this opportunity further and explore how we can work together to make the NeVo Tower a resounding success.
Thank you for considering this opportunity. I look forward to the possibility of working together.
Best regards,
[Your Name]
[Your Position]
[Your Contact Information]

## Legal
Partnership Agreement for NeVo Tower
This Partnership Agreement ("Agreement") is made effective as of the date of last signature ("Effective Date"), between Tykun Luxury Ltd., a Florida limited liability company ("General Partner"), and [Insert Partner Name] ("Partner"), collectively the "Parties."
WHEREAS, General Partner is developing the NeVo Tower, a 24-story (23 floors + rooftop) mixed-use condominium project at 1580 79th Street JFK Causeway, North Bay Village, FL 33124, with construction commencing Q3 2026 and targeting completion by Q3 2029; and
WHEREAS, Partner will contribute services or materials to the project in exchange for equitable profit-sharing and other benefits, as part of a cooperative development model.
NOW, THEREFORE, the Parties agree as follows:
Partnership Scope
1.1 Partner’s Role: Partner shall provide services or materials as detailed in Exhibit A (Scope of Work), attached and incorporated herein, valued at market rates as agreed by the Parties. These contributions serve as Partner’s investment in the NeVo Tower project.
1.2 Project Overview: NeVo Tower is a $91.3M development (total cost) with projected sales revenue of $185,324,100, comprising 260,775 sq. ft. (gross), 160,627 sq. ft. (net salable), 55 condominiums, 20 hospitality suites, 2 commercial spaces, a synagogue, a mikvah, and a rooftop restaurant. Construction adheres to Florida Building Code and Miami-Dade County standards, with a 36-month completion timeline from Q3 2026. The synagogue/mikvah will be relocated temporarily at a cost of $300,000 (funded by General Partner), and sold at cost to avoid losses.
1.3 Governance: Partner shall have no decision-making authority unless otherwise agreed in writing, with General Partner retaining sole project management control.
Partnership Benefits
Partner shall receive:
2.1 Profit-Sharing: Partner shall receive a pro-rata share of the project’s net profits ($94,024,100, defined as gross sales revenue minus project costs per Exhibit B: Project Budget), based on the market value of contributions as specified in Exhibit A. To fairly reward earlier contributions (higher risk), a time-weighted preferred return of 8% annualized accrues on the contribution value from the date of contribution (calculated quarterly, non-compounding for simplicity). This "interest-like" return is paid first from available cash (waterfall Tier 1). Remaining profits are then distributed pro-rata (Tier 2). Cash partners ($34M from 20 buyers) receive the same treatment, with profits based on their Average Daily Balance. Distributions occur quarterly starting Month 18, triggered by sales exceeding 20% increments of salable area (32,125 NSF per 20%; full at 160,627 NSF) or when cumulative cash exceeds $5M, as detailed in Exhibit C: Profit Distribution Schedule. All distributions are subject to independent audit by the accountant partner.
2.2 Accelerated Delivery: The project’s self-financing model eliminates lender approvals, reducing costs by up to 20% per square foot and enabling completion by Q3 2029.
2.3 Land Contribution: General Partner contributes $14M in unencumbered land, warranted free of liens or disputes (treated equally in profit-sharing).
2.4 Accelerated Sales: Self-financing options for buyers expedite sales, starting in Month 1 for cash partners.
2.5 Flexible Shares: Partner may transfer profit-sharing rights with General Partner’s prior written consent, subject to a right of first refusal.
2.6 Tax Benefits: Subject to applicable tax laws, Partner may claim depreciation or other benefits for qualifying contributions, as determined by a tax professional.
2.7 Exclusive Pricing: Partner may purchase up to 2 units at a 20% discount off market rates, subject to availability and General Partner approval.
2.8 Future Opportunities: Partner receives priority consideration for future Tykun Luxury Ltd. projects, subject to mutual agreement.
2.9 Lower Risk: Contributions in services/materials minimize Partner’s financial exposure.
2.10 Increased Visibility: Partner’s business gains exposure through project marketing and collaboration with industry professionals.
2.11 Interim Payments: Partner may receive milestone-based reimbursements for out-of-pocket expenses, as agreed in Exhibit A.
Partner’s Obligations
3.1 Performance: Partner shall perform contributions professionally, timely, and per Exhibit A, with corrective action required within 15 days of notice of deficiencies.
3.2 Compliance: Partner shall comply with all applicable laws, Florida Building Code, and Miami-Dade County standards, bearing costs of correcting non-compliant work unless caused by General Partner.
3.3 Documentation: Partner shall maintain detailed records of contributions and submit them quarterly to General Partner.
3.4 Insurance: Partner shall maintain general liability and professional liability insurance (as applicable), with minimum coverage of $2M, naming General Partner as an additional insured.
General Partner’s Obligations
4.1 Project Management: General Partner shall oversee project execution, secure permits, and ensure regulatory compliance, including the $300,000 synagogue relocation.
4.2 Profit Distribution: General Partner shall distribute profits transparently per Section 2.1 and Exhibit C, within 30 days of quarterly milestones.
4.3 Land Contribution: General Partner warrants the $14M land contribution is free of liens, encumbrances, or disputes.
4.4 Transparency: General Partner shall provide quarterly financial and progress reports, including sales, costs, and construction milestones, accessible via AI-powered tools.
4.5 Financing: General Partner shall arrange self-financing options for buyers to accelerate sales.
Confidentiality
Partner shall keep proprietary project information (e.g., financial data, design plans, marketing strategies) confidential, except for information that is publicly available, independently obtained, or required by law. Upon termination, Partner shall return or destroy confidential materials. This obligation survives termination.
Term and Termination
6.1 Term: This Agreement begins on the Effective Date and continues until project completion (est. Q3 2029) or mutual consent.
6.2 Termination: Either Party may terminate for material breach (e.g., failure to perform obligations under Exhibit A for 30 days after written notice) if uncured within 30 days. Partner retains profit-sharing rights for contributions made prior to termination, proportional to completed work.
6.3 Force Majeure: Neither Party is liable for delays due to unforeseen events (e.g., natural disasters, regulatory changes), with notice required within 10 days.
Dispute Resolution
Disputes shall first undergo mediation in Miami, FL. If unresolved within 30 days, disputes proceed to binding arbitration in Miami, FL, under American Arbitration Association rules. Costs are shared equally unless the arbitrator awards costs to the prevailing party. Florida law governs, excluding conflict-of-law principles. The Parties consent to jurisdiction in Miami, FL. Injunctive relief may be sought for confidentiality breaches.
Miscellaneous
8.1 Entire Agreement: This Agreement, including Exhibits A–C, constitutes the entire agreement. Amendments require written consent of both Parties.
8.2 Non-Assignment: Neither Party may assign this Agreement without the other’s written consent, except General Partner may assign to an affiliate with prior notice.
8.3 Indemnification: Each Party shall indemnify the other for damages caused by its negligence or breach, subject to a cap of $5M, excluding consequential damages.
8.4 Insurance: General Partner shall maintain general liability insurance of at least $2M.
8.5 Notices: Notices shall be sent to the contact information below, effective upon receipt.
8.6 Severability: Invalid provisions do not affect the Agreement’s remainder.
8.7 Change Orders: Changes to Partner’s scope of work require mutual written agreement, with adjustments to profit-sharing as needed.
IN WITNESS WHEREOF, the Parties have executed this Agreement on the Effective Date.
Tykun Luxury Ltd.
By: _________________________
Name: Eli
Title: Managing Member
Date: _________________________
Contact: 1580 79th Street JFK Causeway, North Bay Village, FL 33124, Attn: Eli, 305-905-5068, tykunluxury@gmail.com
Partner
By: _________________________
Name: [Insert Partner Name]
Title: [Insert Partner Title]
Date: _________________________
Contact: [Insert Partner Contact Info]
Exhibits (to be attached):
Exhibit A: Scope of Work – Details Partner’s contributions, timelines, and valuation (market rates negotiated by GP, partners, and reps for best pricing).
Exhibit B: Project Budget – Outlines $91.3M cost, including $77M development ($500/sf base, reduced 20% via in-kind), $14M land, $4.5M-$7.6M synagogue/mikvah (sold at cost), and $300k relocation.
Exhibit C: Profit Distribution Schedule – Specifies waterfall: Tier 1: 8% preferred return (accrued quarterly from contribution date; e.g., $1M contributed Month 1 accrues ~$200k over 36 months at 8%). Tier 2: Pro-rata split of remaining $94M profits. Triggers: Quarterly post-Month 18 at 20% sales increments (32,125 NSF each) or $5M+ cash. Accountant audits; example: At 40% sales, distribute accrued preferred + 40% of pro-rata profits.
Fair Profit-Sharing System
This system ensures fairness by rewarding early/risky contributions without overcomplicating. It's inspired by real estate JV "waterfalls" (tiered distributions) and contribution-based models like Shapley Value, where profits are allocated proportionally but with a time/risk premium.
Preferred Return (Interest-Like Premium): All contributions (services, materials, cash, land) accrue an 8% annualized return from the contribution date. This is time-weighted: Earlier partners earn more (e.g., a $1M contribution in Month 1 accrues for 36 months; later one for fewer). Calculated quarterly (non-compounding) by the accountant partner. Paid first from available cash (Tier 1 in waterfall). Rate based on typical JV preferred returns (8-12%).
Pro-Rata Profits: After preferred returns, remaining profits (~$94M total) are split proportionally to contribution value (e.g., if total contributions = $91.3M, a $1M partner gets ~1.1%).
Payout Timing (Cutoffs): Quarterly starting Month 18, not monthly (to reduce costs). Triggers: Every 20% of salable NSF sold (32,125 NSF; e.g., 20% = partial distribution of accrued preferred + 20% pro-rata profits) or when cumulative cash > $5M. This allows incremental payouts before full sales, using net cash flow. Full reconciliation at project end. If cash is short, preferred rolls over.
Example: Assume $10M total contributions by Month 12. Partner A ($2M in Month 1) accrues ~$480k preferred over 36 months. At 40% sales (Month ~24, ~$30M cash available), distribute accrued preferred proportionally, then 40% of their pro-rata profits.
This balances risk (early gets more via time accrual) with equity, audited for transparency.
Cash Flow Model
I modeled a 36-month projection using Python (pandas). Assumptions:
Cash partners: $34M evenly over Months 1-6 (~$5.7M/month; treated as inflows for preferred unit purchases).
Remaining sales: $151.3M evenly over Months 18-36 (~$8M/month).
Cash outflows: $300k relocation (Month 1); assume 50% of $77M construction is cash ($38.5M, ~$1.07M/month evenly); land/synagogue in-kind (no cash out).
Net: Inflows - outflows; cumulative tracks available cash for distributions.
The model shows negative net early (due to costs), positive from Month 18. Cumulative reaches ~$146.5M (excess cash after cash costs; full profit $94M accounts for in-kind).
| Month | Cash Inflow | Cash Outflow | Net Cash | Cumulative Cash
| 1 | 5666667 | 1369444 | 4297222 | 4297222
| 2 | 5666667 | 1069444 | 4597222 | 8894444
| 3 | 5666667 | 1069444 | 4597222 | 13491667
| 4 | 5666667 | 1069444 | 4597222 | 18088889
| 5 | 5666667 | 1069444 | 4597222 | 22686111
| 6 | 5666667 | 1069444 | 4597222 | 27283333
| 7 | 0 | 1069444 | -1069444 | 26213889
| 8 | 0 | 1069444 | -1069444 | 25144444
| 9 | 0 | 1069444 | -1069444 | 24075000
| 10 | 0 | 1069444 | -1069444 | 23005556
| 11 | 0 | 1069444 | -1069444 | 21936111
| 12 | 0 | 1069444 | -1069444 | 20866667
| 13 | 0 | 1069444 | -1069444 | 19797222
| 14 | 0 | 1069444 | -1069444 | 18727778
| 15 | 0 | 1069444 | -1069444 | 17658333
| 16 | 0 | 1069444 | -1069444 | 16588889
| 17 | 0 | 1069444 | -1069444 | 15519444
| 18 | 7964426 | 1069444 | 6894982 | 22414426
| 19 | 7964426 | 1069444 | 6894982 | 29309408
| 20 | 7964426 | 1069444 | 6894982 | 36204390
| 21 | 7964426 | 1069444 | 6894982 | 43099372
| 22 | 7964426 | 1069444 | 6894982 | 49994354
| 23 | 7964426 | 1069444 | 6894982 | 56889336
| 24 | 7964426 | 1069444 | 6894982 | 63784318
| 25 | 7964426 | 1069444 | 6894982 | 70679299
| 26 | 7964426 | 1069444 | 6894982 | 77574281
| 27 | 7964426 | 1069444 | 6894982 | 84469263
| 28 | 7964426 | 1069444 | 6894982 | 91364245
| 29 | 7964426 | 1069444 | 6894982 | 98259227
| 30 | 7964426 | 1069444 | 6894982 | 105154209
| 31 | 7964426 | 1069444 | 6894982 | 112049191
| 32 | 7964426 | 1069444 | 6894982 | 118944173
| 33 | 7964426 | 1069444 | 6894982 | 125839154
| 34 | 7964426 | 1069444 | 6894982 | 132734136
| 35 | 7964426 | 1069444 | 6894982 | 139629118
| 36 | 7964426 | 1069444 | 6894982 | 146524100

## Cost DrillDown
INSURANCE ON 77M HARD + SOFT COSTS |  | 77000000
Category | Description | Low Estimate |  | Average Estimate
Builder's Risk | Covers building materials, site damage, theft, weather (key in FL hurricanes) | 770000 | 1% | 1925000 | 2.5%
General Liability | Protects against third-party claims (e.g., injuries, property damage) | 770000 | 1% | 1155000 | 1.5%
Workers' Compensation | For on-site injuries/illnesses (based on ~$19.25M payroll at 2-5% rate) | 385000 | 0.5% | 577500 | 0.75%
Professional Liability | For design errors (e.g., architects/engineers; often required for high-rises) | 385000 | 0.5% | 770000 | 1%
Other (Umbrella, Bonds) | Excess coverage, performance bonds, etc. | 385000 | 0.5% | 385000 | 0.5%
Total | Overall project insurance (as % of $77M) | 2695000 | 3.5% | 4812500 | 6.25%

## Takeoff
Budget Takeoff Table (Structure & MEP & Administrative/Soft Costs Focus, Average Prices) |  |  | 260775 | Gross SF
Category | Item | Unit | Quantity | Research Unit Cost | Research Total Cost | Source (Basis for Research) | Cost per SF (GSF)
Structure | Land clearing and grading | SF | 20000 | 1.5 | 30000 | ProMatcher - Miami clearing $1.50/sf avg. | 0.11504
Structure | Excavation | SF | 20000 | 3 | 60000 | Homewyse/ENR - Excavation ~$4/sf adjusted; ENR data | 0.23008
Structure | Soil testing and geotechnical | Lot | 1 | 50000 | 50000 | EstimatorFlorida - Geotech $50k | 0.19174
Structure | Dewatering | Lot | 1 | 125000 | 125000 | RSMeans/FL PSC - High water table $100k-150k | 0.47934
Structure | Drilled shaft/caisson piles | Each | 70 | 12000 | 840000 | Gordian/ENR - Piles $10k-15k | 3.2212
Structure | Concrete (piles, caps, beams) | CY | 3920 | 192 | 752640 | EstimatorFlorida - Concrete $175-210/CY avg. $192 | 2.8862
Structure | Rebar reinforcement (foundation) | Tons | 392 | 1000 | 392000 | HomeGuide - Rebar $800-1200/ton avg. $1000 | 1.5032
Structure | Formwork and shoring | SF | 20000 | 4.7 | 93200 | Homewyse - Formwork $4.20-5.12/sf avg. $4.7 | 0.3574
Structure | Concrete (shear walls/core) | CY | 1800 | 192 | 345600 | EstimatorFlorida - $192/CY | 1.3253
Structure | Rebar reinforcement (shear walls) | Tons | 270 | 1000 | 270000 | HomeGuide - $1000/ton | 1.0354
Structure | Formwork (shear walls) | SF | 70600 | 4.7 | 329000 | Homewyse - $4.7/sf | 1.2616
Structure | Water line connection | Lot | 1 | 50000 | 50000 | General FL estimates | 0.19174
Structure | Sewer line connection | Lot | 1 | 50000 | 50000 | General FL estimates | 0.19174
Structure | Stormwater drainage | Lot | 1 | 75000 | 75000 | General FL estimates | 0.2876
Structure | Gas line connection | Lot | 1 | 30000 | 30000 | General FL estimates | 0.11504
Structure | Trenching and backfill | SF | 20000 | 3 | 60000 | ProMatcher - Trenching ~$3/sf | 0.23008
Structure | 50-ton cranes | Each | 2 | 225000 | 450000 | EquipmentWatch/FL PSC - Rental $200k-250k avg. $225k | 1.7256
Structure | Pre-cast columns | Each | 230 | 2000 | 460000 | General estimates | 1.764
Structure | Concrete (slabs, floors 2–23 + rooftop) | CY | 8700 | 192 | 1670400 | EstimatorFlorida - $192/CY | 6.4055
Structure | Rebar reinforcement (slabs) | Tons | 1305 | 1000 | 1305000 | HomeGuide - $1000/ton | 5.0043
Structure | Formwork (slabs) | SF | 260685 | 4.7 | 1214792 | Homewyse - $4.7/sf | 4.6584
Structure | Crane labor | Hours | 1790.4 | 50 | 89520 | BLS/ENR - Labor $50/hr avg. | 0.34328
Structure | Slab pouring labor | Hours | 18270 | 50 | 913500 | BLS/ENR - $50/hr | 3.503
Structure | Column installation labor | Hours | 1840 | 50 | 92000 | BLS/ENR - $50/hr | 0.35279
Structure | Efficiency bonus | Lot | 1 | 100000 | 100000 | General estimates | 0.38347
Structure | Concrete (floor 1 slab, columns) | CY | 605 | 192 | 116160 | EstimatorFlorida - $192/CY | 0.44544
Structure | Rebar reinforcement (floor 1) | Tons | 90.8 | 1000 | 90800 | HomeGuide - $1000/ton | 0.34819
Structure | Formwork (floor 1) | SF | 13125 | 4.7 | 61163 | Homewyse - $4.7/sf | 0.23454
Structure | Labor (floor 1) | Hours | 908 | 50 | 45400 | BLS/ENR - $50/hr | 0.1741
Structure | Concrete (floors 2–23 slabs, columns) | CY | 8075 | 192 | 1550400 | EstimatorFlorida - $192/CY | 5.9454
Structure | Rebar reinforcement (floors 2–23) | Tons | 1211.3 | 1000 | 1211300 | HomeGuide - $1000/ton | 4.645
Structure | Formwork (floors 2–23) | SF | 238950 | 4.7 | 1113507 | Homewyse - $4.7/sf | 4.27
Structure | Labor (floors 2–5, per floor) | Hours | 1350 | 50 | 67500 | BLS/ENR - $50/hr | 0.25884
Structure | Labor (floors 6–14, per floor) | Hours | 932 | 50 | 46600 | BLS/ENR - $50/hr | 0.1787
Structure | Labor (floors 15–23, per floor) | Hours | 762 | 50 | 38100 | BLS/ENR - $50/hr | 0.1461
Structure | Concrete (rooftop slab, columns) | CY | 368 | 192 | 70656 | EstimatorFlorida - $192/CY | 0.27095
Structure | Rebar reinforcement (rooftop) | Tons | 55.2 | 1000 | 55200 | HomeGuide - $1000/ton | 0.21168
Structure | Formwork (rooftop) | SF | 8700 | 4.7 | 40542 | Homewyse - $4.7/sf | 0.15547
Structure | Labor (rooftop) | Hours | 600 | 50 | 30000 | BLS/ENR - $50/hr | 0.11504
Structure Sub-Total |  |  |  |  | 14384980 | - | 55.1624
MEP | HVAC Systems (Separate per unit, smart controls) | Unit | 75 | 57500 | 4312500 | Homewyse/ENR - Separate IoT HVAC $50k-65k/unit avg. $57.5k | 16.5372
MEP | Electrical Wiring & Systems (Separate metering, smart switches) | Unit | 75 | 34500 | 2587500 | EstimatorFlorida/RSMeans - IoT wiring $30k-40k/unit avg. $34.5k | 9.9223
MEP | Plumbing Fixtures & Pipes (Submetered water) | Unit | 75 | 23000 | 1725000 | HomeGuide/ENR - Submetered $20k-25k/unit avg. $23k | 6.6149
MEP | Elevators (6 units: 3 full, 2 comm, 1 service) | Each | 6 | 200000 | 1200000 | Gordian/ENR - High-rise $150k-250k avg. $200k | 4.6017
MEP | Fire Suppression Systems (Per unit/common) | SF | 260775 | 6 | 1564650 | RSMeans - Separated $5-8/SF avg. $6 | 6
MEP | Smart Door Locks/Curtains/Controls (IoT per unit) | Unit | 75 | 1150 | 86250 | HomeAdvisor - Smart home $800-1.5k/unit avg. $1.15k | 0.33074
MEP | Utility Separation Premium (Metering/IoT integration) | Lot | 1 | 2300000 | 2300000 | YieldStreet - 15% add for full IoT/separation | 8.8199
MEP Sub-Total |  |  |  |  | 13775900 | - | 52.8268
Soft Costs | Design & Engineering (Architect/Engineer) | Lot | 1 | 3570000 | 3570000 | Feldman Equities - 6% low of 6-8% hard costs ($59.5M *6%) | 13.69
Soft Costs | Permitting & Fees (Reduced 15% via amenities) | Lot | 1 | 2730000 | 2730000 | Multifamily Loans - 3% low of 3-5% total ($91M *3%) | 10.4688
Soft Costs | Marketing & Sales (Pre-sales, broker fees) | Lot | 1 | 1820000 | 1820000 | YieldStreet - 2% low of 2-4% total ($91M *2%) | 6.9792
Soft Costs | Legal & Insurance (Contracts, liability) | Lot | 1 | 2730000 | 2730000 | Home Builder Digest - 3% low of 3-5% ($91M *3%) | 10.4688
Soft Costs | Project Management & Overhead (Admin, AI tools) | Lot | 1 | 910000 | 910000 | SolutionsGC - 1% low of 1-2% ($91M *1%) | 3.4896
Soft Costs | Contingencies & Miscellaneous (8% buffer) | Lot | 1 | 4550000 | 4550000 | Norada Real Estate - 5% low of 5-10% ($91M *5%) | 17.448
Soft Costs Sub-Total |  |  |  |  | 16310000 | - | 62.5443
Grand Total |  |  |  |  | 44470880 | - | 170.5335

## TO Carlos Pre-Built
Dear Carlos,
Below is a detailed description of the work required for the NeVo Tower project, including the scope, budget breakdown based on the takeoff quantities and average 2025 Miami prices (totaling $8,245,050 for structure-related hard costs which aligns with the project's structure focus budget (see takeoff table below for detailed costs in materials/labor/equipment)), and a table summarizing the site's dimensions, floor plates, and heights. This is provided in English, Spanish, and German for clarity.
English Description
As the contractor for the NeVo Tower, a 24-story mixed-use luxury condominium in North Bay Village, FL, your scope focuses on the hard costs execution. This includes site preparation (clearing 20,000 SF, grading, excavating to 20-40 ft with shoring in sandy soils, soil testing, and dewatering for ~10 weeks); foundation (installing 70 drilled shaft piles at 20-40 ft, pouring 3,920 CY of 8,000 psi concrete, placing 392 tons of rebar, and formwork for 20,000 SF); shear walls and shafts (pouring 1,800 CY of concrete with variable elevator configurations—3 full elevators from floors 1-24, 2 commercial from 1-5, 1 from 1-2—plus 270 tons of rebar and formwork for 70,600 SF); rough ground utilities (connecting water, sewer, stormwater, and gas lines with 20,000 SF trenching); and structure erection (operating 2 50-ton cranes for 20 weeks, installing 230 pre-cast columns for floors 2-23, installing ~2,065 pre-cast planks for slabs on floors 2-23 and rooftop (Floor 1 cast-in-place with 605 CY concrete, 90.8 tons rebar, and 13,125 SF formwork), placing 652.5 tons rebar (reduced for pre-cast), and formwork for 119,018 SF (reduced 67% for pre-cast areas)). All work must comply with Florida Building Code and Miami-Dade standards, emphasizing waterfront resilience and luxury specs over 36 months from Q3 2026.
Budget Takeoff Table (Structure Focus, Average Prices)
Category | Item | Unit | Quantity | Unit Cost (Avg. Miami 2025) | Total Cost
Site Preparation | Land clearing and grading | SF | 20000 | 1.5 | 30000
| Excavation | SF | 20000 | 2.5 | 50000
| Soil testing and geotechnical | Lot | 1 | 50000 | 50000
| Dewatering | Lot | 1 | 100000 | 100000
Foundation | Drilled shaft/caisson piles | Each | 70 | 10000 | 700000
| Concrete (piles, caps, beams) | CY | 3920 | 160 | 627200
| Rebar reinforcement | Tons | 392 | 1200 | 470400
| Formwork and shoring | SF | 20000 | 6 | 120000
Shear Walls (incl. Shafts) | Concrete (core, elevators, staircases) | CY | 1800 | 160 | 288000
| Rebar reinforcement | Tons | 270 | 1200 | 324000
| Formwork | SF | 70600 | 6 | 423600
Rough Ground Utilities | Water line connection | Lot | 1 | 50000 | 50000
| Sewer line connection | Lot | 1 | 50000 | 50000
| Stormwater drainage | Lot | 1 | 75000 | 75000
| Gas line connection | Lot | 1 | 30000 | 30000
| Trenching and backfill | SF | 20000 | 3 | 60000
Structure (Crane & Labor) | 50-ton cranes | Each | 2 | 250000 | 500000
| Pre-cast columns | Each | 230 | 2000 | 460000
| Pre-cast slabs/planks (floors 2-23 + rooftop) | Each | 2065 | 3000 | 6195000
| Rebar reinforcement (reduced for pre-cast) | Tons | 652.5 | 1200 | 783000
| Formwork (reduced for pre-cast) | SF | 119018 | 6 | 714108
| Crane labor (extended for pre-cast handling) | Hours | 2148.48 | 60 | 128909
| Slab/plank installation labor | Hours | 6195 | 60 | 371700
| Column installation labor | Hours | 1840 | 60 | 110400
| Efficiency bonus | Lot | 1 | 100000 | 100000
Structure (Floor 1 - Cast-in-Place) | Concrete (slab, columns) | CY | 605 | 160 | 96800
| Rebar reinforcement | Tons | 90.8 | 1200 | 108960
| Formwork | SF | 13125 | 6 | 78750
| Labor | Hours | 908 | 60 | 54480
Grand Total |  |  |  |  | 8245050
Dimensions Table
Floor/Level | Height (ft) | Width (ft) | Length (ft) | GSF (sq. ft.) | Notes
Site/Lot | N/A | 100 | 200 | 20000 | Overall lot size; man-made island with high water table.
Floor 1 | 20 | 75 | 175 | 13125 | Lobby, retail, mikvah; reduced common area.
Floor 2 | 12 | 90 | 175 | 15750 | Synagogue.
Floors 3-5 | 8.25 | 90 | 175 | 15,750 each (47,250 total) | Parking with EV/ADA.
Floor 6 | 10 | 70 | 155 | 10850 | Hospitality suites + gym (2,000 SF reduced).
Floors 7-14 | 10 | 70 | 155 | 10,850 each (86,800 total) | Residential condos.
Floors 15-22 | 10 | 60 | 145 | 8,700 each (69,600 total) | Mixed residential/hospitality.
Floor 23 | 13.25 | 60 | 145 | 8700 | Penthouse.
Rooftop | N/A | 60 | 145 | 8700 | Pool/spa/restaurant.
Total Building Height | 240 | - | - | - | From ground to rooftop; complies with zoning.
Descripción del Trabajo para el Contratista "Carlos" (Español)
Como contratista del NeVo Tower, un condominio de lujo mixto de 24 pisos en North Bay Village, FL, su alcance se centra en la ejecución de costos duros. Esto incluye la preparación del sitio (limpieza de 20,000 SF, nivelación, excavación a 20-40 ft con apuntalamiento en suelos arenosos, pruebas de suelo y desagüe por ~10 semanas); cimentación (instalación de 70 pilotes perforados a 20-40 ft, vertido de 3,920 CY de concreto 8,000 psi, colocación de 392 toneladas de rebar y encofrado para 20,000 SF); muros de corte y ejes (vertido de 1,800 CY de concreto con configuraciones variables de ascensores—3 completos de pisos 1-24, 2 comerciales de 1-5, 1 de 1-2—más 270 toneladas de rebar y encofrado para 70,600 SF); utilidades subterráneas rough (conexión de líneas de agua, alcantarillado, drenaje pluvial y gas con zanjas de 20,000 SF); y erección de estructura (operación de 2 grúas de 50 toneladas por 20 semanas, instalación de 230 columnas prefabricadas para pisos 2-23, instalación de ~2,065 losas prefabricadas para pisos 2-23 y azotea (Piso 1 vertido in situ con 605 CY de concreto, 90.8 toneladas de rebar y 13,125 SF de encofrado), colocación de 652.5 toneladas de rebar (reducido para prefabricado), y encofrado para 119,018 SF (reducido 67% para áreas prefabricadas)). Todo el trabajo cumple con el Código de Construcción de Florida y estándares de Miami-Dade, enfatizando resiliencia costera y especificaciones de lujo durante 36 meses desde Q3 2026.
Tabla de Presupuesto de Despegue (Enfoque en Estructura, Precios Promedio)
Categoría | Ítem | Unidad | Cantidad | Costo Unitario (Promedio Miami 2025) | Costo Total
Preparación del Sitio | Limpieza y nivelación del terreno | SF | 20000 | 1.5 | 30000
| Excavación | SF | 20000 | 2.5 | 50000
| Pruebas de suelo y geotécnicas | Lote | 1 | 50000 | 50000
| Desagüe | Lote | 1 | 100000 | 100000
Cimentación | Pilotes perforados/caisson | Cada | 70 | 10000 | 700000
| Concreto (pilotes, tapas, vigas) | CY | 3920 | 160 | 627200
| Refuerzo de rebar | Toneladas | 392 | 1200 | 470400
| Encofrado y apuntalamiento | SF | 20000 | 6 | 120000
Muros de Corte (incl. Ejes) | Concreto (núcleo, ascensores, escaleras) | CY | 1800 | 160 | 288000
| Refuerzo de rebar | Toneladas | 270 | 1200 | 324000
| Encofrado | SF | 70600 | 6 | 423600
Utilidades Subterráneas Rough | Conexión de línea de agua | Lote | 1 | 50000 | 50000
| Conexión de línea de alcantarillado | Lote | 1 | 50000 | 50000
| Drenaje pluvial | Lote | 1 | 75000 | 75000
| Conexión de línea de gas | Lote | 1 | 30000 | 30000
| Zanjas y relleno | SF | 20000 | 3 | 60000
Estructura (Grúa y Mano de Obra) | Grúas de 50 toneladas | Cada | 2 | 250000 | 500000
| Columnas prefabricadas | Cada | 230 | 2000 | 460000
| Losas/losas prefabricadas (pisos 2-23 + azotea) | Cada | 2065 | 3000 | 6195000
| Refuerzo de rebar (reducido para prefabricado) | Toneladas | 652.5 | 1200 | 783000
| Encofrado (reducido para prefabricado) | SF | 119018 | 6 | 714108
| Mano de obra de grúa (extendida para manejo prefabricado) | Horas | 2148.48 | 60 | 128909
| Mano de obra de instalación de losas/losas | Horas | 6195 | 60 | 371700
| Mano de obra de instalación de columnas | Horas | 1840 | 60 | 110400
| Bono de eficiencia | Lote | 1 | 100000 | 100000
Estructura (Piso 1 - Vertido In Situ) | Concreto (losa, columnas) | CY | 605 | 160 | 96800
| Refuerzo de rebar | Toneladas | 90.8 | 1200 | 108960
| Encofrado | SF | 13125 | 6 | 78750
| Mano de obra | Horas | 908 | 60 | 54480
Total General |  |  |  |  | 8245050
Tabla de Dimensiones
Piso/Nivel | Altura (ft) | Ancho (ft) | Largo (ft) | GSF (sq. ft.) | Notas
Sitio/Lote | N/A | 100 | 200 | 20000 | Tamaño general del lote; isla artificial con alto nivel freático.
Piso 1 | 20 | 75 | 175 | 13125 | Vestíbulo, retail, mikvah; área común reducida.
Piso 2 | 12 | 90 | 175 | 15750 | Sinagoga.
Pisos 3-5 | 8.25 | 90 | 175 | 15,750 cada uno (47,250 total) | Estacionamiento con EV/ADA.
Piso 6 | 10 | 70 | 155 | 10850 | Suites de hospitalidad + gimnasio (2,000 SF reducido).
Pisos 7-14 | 10 | 70 | 155 | 10,850 cada uno (86,800 total) | Condominios residenciales.
Pisos 15-22 | 10 | 60 | 145 | 8,700 cada uno (69,600 total) | Residencial/hospitalidad mixta.
Piso 23 | 13.25 | 60 | 145 | 8700 | Penthouse.
Azotea | N/A | 60 | 145 | 8700 | Piscina/spa/restaurante.
Altura Total del Edificio | 240 | - | - | - | Desde el suelo hasta la azotea; cumple con zonificación.
Beschreibung der Arbeit für den Auftragnehmer "Carlos" (Deutsch)
Als Auftragnehmer für den NeVo Tower, einem 24-stöckigen gemischt genutzten Luxus-Kondominium in North Bay Village, FL, liegt Ihr Umfang auf der Ausführung der harten Kosten. Dies umfasst die Geländevorbereitung (Räumung von 20.000 SF, Nivellierung, Ausgrabung bis 20-40 ft mit Stützung in sandigen Böden, Bodenuntersuchungen und Entwässerung für ~10 Wochen); Fundamentarbeiten (Einbau von 70 gebohrten Pfählen bis 20-40 ft, Gießen von 3.920 CY 8.000 psi Beton, Verlegung von 392 Tonnen Bewehrung und Schalung für 20.000 SF); Schubwände und Schächte (Gießen von 1.800 CY Beton mit variablen Aufzugs-Konfigurationen—3 volle Aufzüge von Etagen 1-24, 2 kommerzielle von 1-5, 1 von 1-2—plus 270 Tonnen Bewehrung und Schalung für 70.600 SF); rohe unterirdische Versorgungsleitungen (Anschluss von Wasser-, Abwasser-, Regenwasser- und Gasleitungen mit Graben von 20.000 SF); und Strukturbau (Betrieb von 2 50-Tonnen-Kränen für 20 Wochen, Einbau von 230 vorgefertigten Säulen für Etagen 2-23, Einbau von ~2.065 vorgefertigten Platten für Platten in Etagen 2-23 und Dach (Etage 1 gegossen vor Ort mit 605 CY Beton, 90.8 Tonnen Bewehrung und 13.125 SF Schalung), Verlegung von 652.5 Tonnen Bewehrung (reduziert für vorgefertigt), und Schalung für 119.018 SF (reduziert 67% für vorgefertigte Bereiche)). Alle Arbeiten entsprechen dem Florida Building Code und Miami-Dade-Standards, mit Fokus auf Küstenresilienz und Luxusausstattung über 36 Monate ab Q3 2026.
Tabelle des Budget-Despegue (Fokus auf Struktur, Durchschnittspreise)
Kategorie | Artikel | Einheit | Menge | Einheitspreis (Durchschnitt Miami 2025) | Gesamtkosten
Geländevorbereitung | Räumung und Nivellierung des Geländes | SF | 20000 | 1.5 | 30000
| Ausgrabung | SF | 20000 | 2.5 | 50000
| Bodenuntersuchungen und geottechnisch | Lot | 1 | 50000 | 50000
| Entwässerung | Lot | 1 | 100000 | 100000
Fundament | Gebohrte Pfähle/Caissons | Jeder | 70 | 10000 | 700000
| Beton (Pfähle, Kappen, Balken) | CY | 3920 | 160 | 627200
| Bewehrung mit Rebar | Tonnen | 392 | 1200 | 470400
| Schalung und Stützung | SF | 20000 | 6 | 120000
Schubwände (inkl. Schächte) | Beton (Kern, Aufzüge, Treppenhäuser) | CY | 1800 | 160 | 288000
| Bewehrung mit Rebar | Tonnen | 270 | 1200 | 324000
| Schalung | SF | 70600 | 6 | 423600
Rohe Unterirdische Versorgungsleitungen | Wasserleitungsanschluss | Lot | 1 | 50000 | 50000
| Abwasserleitungsanschluss | Lot | 1 | 50000 | 50000
| Regenwasserdrainage | Lot | 1 | 75000 | 75000
| Gasleitungsanschluss | Lot | 1 | 30000 | 30000
| Graben und Verfüllung | SF | 20000 | 3 | 60000
Struktur (Kran & Arbeit) | 50-Tonnen-Kräne | Jeder | 2 | 250000 | 500000
| Vorgefertigte Säulen | Jeder | 230 | 2000 | 460000
| Vorgefertigte Platten/Planken (Etagen 2-23 + Dach) | Jeder | 2065 | 3000 | 6195000
| Bewehrung mit Rebar (reduziert für vorgefertigt) | Tonnen | 652.5 | 1200 | 783000
| Schalung (reduziert für vorgefertigt) | SF | 119018 | 6 | 714108
| Kranarbeit (erweitert für vorgefertigte Handhabung) | Stunden | 2148.48 | 60 | 128909
| Platten/Planken-Installationsarbeit | Stunden | 6195 | 60 | 371700
| Säulen-Installationsarbeit | Stunden | 1840 | 60 | 110400
| Effizienzbonus | Lot | 1 | 100000 | 100000
Struktur (Etage 1 - Gegossen Vor Ort) | Beton (Platte, Säulen) | CY | 605 | 160 | 96800
| Bewehrung mit Rebar | Tonnen | 90.8 | 1200 | 108960
| Schalung | SF | 13125 | 6 | 78750
| Arbeit | Stunden | 908 | 60 | 54480
Gesamtsumme |  |  |  |  | 8245050
Tabelle der Dimensionen
Etage/Ebene | Höhe (ft) | Breite (ft) | Länge (ft) | GSF (sq. ft.) | Notizen
Gelände/Lot | N/A | 100 | 200 | 20000 | Gesamte Lot-Größe; künstliche Insel mit hohem Grundwasserstand.
Etage 1 | 20 | 75 | 175 | 13125 | Lobby, Retail, Mikvah; reduzierte Gemeinschaftsfläche.
Etage 2 | 12 | 90 | 175 | 15750 | Synagoge.
Etagen 3-5 | 8.25 | 90 | 175 | 15,750 je (47,250 total) | Parken mit EV/ADA.
Etage 6 | 10 | 70 | 155 | 10850 | Hospitality-Suiten + Fitnessstudio (2,000 SF reduziert).
Etagen 7-14 | 10 | 70 | 155 | 10,850 je (86,800 total) | Residential-Kondominien.
Etagen 15-22 | 10 | 60 | 145 | 8,700 je (69,600 total) | Gemischte Residential/Hospitality.
Etage 23 | 13.25 | 60 | 145 | 8700 | Penthouse.
Dach | N/A | 60 | 145 | 8700 | Pool/Spa/Restaurant.
Gesamthöhe des Gebäudes | 240 | - | - | - | Vom Boden bis zum Dach; konform mit Zonierung.
Best regards,
Eli (Managing Member, Tykun Luxury Ltd.)

## TO Carlos Cast
Dear Carlos,
Below is a detailed description of the work required for the NeVo Tower project, including the scope, budget breakdown based on the takeoff quantities and average 2025 Miami prices (totaling $9,558,650 for structure-related hard costs which aligns with the project's structure focus budget (see takeoff table below for detailed costs in materials/labor/equipment)), and a table summarizing the site's dimensions, floor plates, and heights. This is provided in English, Spanish, and German for clarity.
English Description
As the contractor for the NeVo Tower, a 24-story mixed-use luxury condominium in North Bay Village, FL, your scope focuses on the hard costs execution. This includes site preparation (clearing 20,000 SF, grading, excavating to 20-40 ft with shoring in sandy soils, soil testing, and dewatering for ~10 weeks); foundation (installing 70 drilled shaft piles at 20-40 ft, pouring 3,920 CY of 8,000 psi concrete, placing 392 tons of rebar, and formwork for 20,000 SF); shear walls and shafts (pouring 1,800 CY of concrete with variable elevator configurations—3 full elevators from floors 1-24, 2 commercial from 1-5, 1 from 1-2—plus 270 tons of rebar and formwork for 70,600 SF); rough ground utilities (connecting water, sewer, stormwater, and gas lines with 20,000 SF trenching); and structure erection (operating 2 50-ton cranes for 20 weeks, installing 230 pre-cast columns, pouring 8,700 CY of concrete for 10" slabs across floors 2-23 and rooftop, placing 1,305 tons of rebar, and formwork for 260,685 SF). All work must comply with Florida Building Code and Miami-Dade standards, emphasizing waterfront resilience and luxury specs over 36 months from Q3 2026.
Budget Takeoff Table (Structure Focus, Average Prices)
Category | Item | Unit | Quantity | Unit Cost (Avg. Miami 2025) | Total Cost
Site Preparation | Land clearing and grading | SF | 20000 | 1.5 | 30000
| Excavation | SF | 20000 | 2.5 | 50000
| Soil testing and geotechnical | Lot | 1 | 50000 | 50000
| Dewatering | Lot | 1 | 100000 | 100000
Foundation | Drilled shaft/caisson piles | Each | 70 | 10000 | 700000
| Concrete (piles, caps, beams) | CY | 3920 | 160 | 627200
| Rebar reinforcement | Tons | 392 | 1200 | 470400
| Formwork and shoring | SF | 20000 | 6 | 120000
Shear Walls (incl. Shafts) | Concrete (core, elevators, staircases) | CY | 1800 | 160 | 288000
| Rebar reinforcement | Tons | 270 | 1200 | 324000
| Formwork | SF | 70600 | 6 | 423600
Rough Ground Utilities | Water line connection | Lot | 1 | 50000 | 50000
| Sewer line connection | Lot | 1 | 50000 | 50000
| Stormwater drainage | Lot | 1 | 75000 | 75000
| Gas line connection | Lot | 1 | 30000 | 30000
| Trenching and backfill | SF | 20000 | 3 | 60000
Structure (Crane & Labor) | 50-ton cranes | Each | 2 | 250000 | 500000
| Pre-cast columns | Each | 230 | 2000 | 460000
| Concrete (slabs, floors 2–23 + rooftop) | CY | 8700 | 160 | 1392000
| Rebar reinforcement | Tons | 1305 | 1200 | 1566000
| Formwork | SF | 260685 | 6 | 1564110
| Crane labor | Hours | 1790.4 | 60 | 107424
| Slab pouring labor | Hours | 18270 | 60 | 1096200
| Column installation labor | Hours | 1840 | 60 | 110400
| Efficiency bonus | Lot | 1 | 100000 | 100000
Structure (Floor 1) | Concrete (slab, columns) | CY | 605 | 160 | 96800
| Rebar reinforcement | Tons | 90.8 | 1200 | 108960
| Formwork | SF | 13125 | 6 | 78750
| Labor | Hours | 908 | 60 | 54480
Structure (Floors 2–23) | Concrete (slabs, columns) | CY | 8075 | 160 | 1292000
| Rebar reinforcement | Tons | 1211.3 | 1200 | 1453560
| Formwork | SF | 238950 | 6 | 1433700
| Labor (floors 2–5, per floor) | Hours | 1350 | 60 | 81000
| Labor (floors 6–14, per floor) | Hours | 932 | 60 | 55920
| Labor (floors 15–23, per floor) | Hours | 762 | 60 | 45720
Structure (Rooftop) | Concrete (slab, columns) | CY | 368 | 160 | 58880
| Rebar reinforcement | Tons | 55.2 | 1200 | 66240
| Formwork | SF | 8700 | 6 | 52200
| Labor | Hours | 600 | 60 | 36000
Grand Total |  |  |  |  | 9558650
Dimensions Table
Floor/Level | Height (ft) | Width (ft) | Length (ft) | GSF (sq. ft.) | Notes
Site/Lot | N/A | 100 | 200 | 20000 | Overall lot size; man-made island with high water table.
Floor 1 | 20 | 75 | 175 | 13125 | Lobby, retail, mikvah; reduced common area.
Floor 2 | 12 | 90 | 175 | 15750 | Synagogue.
Floors 3-5 | 8.25 | 90 | 175 | 15,750 each (47,250 total) | Parking with EV/ADA.
Floor 6 | 10 | 70 | 155 | 10850 | Hospitality suites + gym (2,000 SF reduced).
Floors 7-14 | 10 | 70 | 155 | 10,850 each (86,800 total) | Residential condos.
Floors 15-22 | 10 | 60 | 145 | 8,700 each (69,600 total) | Mixed residential/hospitality.
Floor 23 | 13.25 | 60 | 145 | 8700 | Penthouse.
Rooftop | N/A | 60 | 145 | 8700 | Pool/spa/restaurant.
Total Building Height | 240 | - | - | - | From ground to rooftop; complies with zoning.
Descripción del Trabajo para el Contratista "Carlos" (Español)
Como contratista del NeVo Tower, un condominio de lujo mixto de 24 pisos en North Bay Village, FL, su alcance se centra en la ejecución de costos duros. Esto incluye la preparación del sitio (limpieza de 20,000 SF, nivelación, excavación a 20-40 ft con apuntalamiento en suelos arenosos, pruebas de suelo y desagüe por ~10 semanas); cimentación (instalación de 70 pilotes perforados a 20-40 ft, vertido de 3,920 CY de concreto 8,000 psi, colocación de 392 toneladas de rebar y encofrado para 20,000 SF); muros de corte y ejes (vertido de 1,800 CY de concreto con configuraciones variables de ascensores—3 completos de pisos 1-24, 2 comerciales de 1-5, 1 de 1-2—más 270 toneladas de rebar y encofrado para 70,600 SF); utilidades subterráneas rough (conexión de líneas de agua, alcantarillado, drenaje pluvial y gas con zanjas de 20,000 SF); y erección de estructura (operación de 2 grúas de 50 toneladas por 20 semanas, instalación de 230 columnas prefabricadas, vertido de 8,700 CY de concreto para losas de 10" en pisos 2-23 y azotea, colocación de 1,305 toneladas de rebar y encofrado para 260,685 SF). Todo el trabajo cumple con el Código de Construcción de Florida y estándares de Miami-Dade, enfatizando resiliencia costera y especificaciones de lujo durante 36 meses desde Q3 2026.
Tabla de Presupuesto de Despegue (Enfoque en Estructura, Precios Promedio)
Categoría | Ítem | Unidad | Cantidad | Costo Unitario (Promedio Miami 2025) | Costo Total
Preparación del Sitio | Limpieza y nivelación del terreno | SF | 20000 | 1.5 | 30000
| Excavación | SF | 20000 | 2.5 | 50000
| Pruebas de suelo y geotécnicas | Lote | 1 | 50000 | 50000
| Desagüe | Lote | 1 | 100000 | 100000
Cimentación | Pilotes perforados/caisson | Cada | 70 | 10000 | 700000
| Concreto (pilotes, tapas, vigas) | CY | 3920 | 160 | 627200
| Refuerzo de rebar | Toneladas | 392 | 1200 | 470400
| Encofrado y apuntalamiento | SF | 20000 | 6 | 120000
Muros de Corte (incl. Ejes) | Concreto (núcleo, ascensores, escaleras) | CY | 1800 | 160 | 288000
| Refuerzo de rebar | Toneladas | 270 | 1200 | 324000
| Encofrado | SF | 70600 | 6 | 423600
Utilidades Subterráneas Rough | Conexión de línea de agua | Lote | 1 | 50000 | 50000
| Conexión de línea de alcantarillado | Lote | 1 | 50000 | 50000
| Drenaje pluvial | Lote | 1 | 75000 | 75000
| Conexión de línea de gas | Lote | 1 | 30000 | 30000
| Zanjas y relleno | SF | 20000 | 3 | 60000
Estructura (Grúa y Mano de Obra) | Grúas de 50 toneladas | Cada | 2 | 250000 | 500000
| Columnas prefabricadas | Cada | 230 | 2000 | 460000
| Concreto (losas, pisos 2–23 + azotea) | CY | 8700 | 160 | 1392000
| Refuerzo de rebar | Toneladas | 1305 | 1200 | 1566000
| Encofrado | SF | 260685 | 6 | 1564110
| Mano de obra de grúa | Horas | 1790.4 | 60 | 107424
| Mano de obra de vertido de losas | Horas | 18270 | 60 | 1096200
| Mano de obra de instalación de columnas | Horas | 1840 | 60 | 110400
| Bono de eficiencia | Lote | 1 | 100000 | 100000
Estructura (Piso 1) | Concreto (losa, columnas) | CY | 605 | 160 | 96800
| Refuerzo de rebar | Toneladas | 90.8 | 1200 | 108960
| Encofrado | SF | 13125 | 6 | 78750
| Mano de obra | Horas | 908 | 60 | 54480
Estructura (Pisos 2–23) | Concreto (losas, columnas) | CY | 8075 | 160 | 1292000
| Refuerzo de rebar | Toneladas | 1211.3 | 1200 | 1453560
| Encofrado | SF | 238950 | 6 | 1433700
| Mano de obra (pisos 2–5, por piso) | Horas | 1350 | 60 | 81000
| Mano de obra (pisos 6–14, por piso) | Horas | 932 | 60 | 55920
| Mano de obra (pisos 15–23, por piso) | Horas | 762 | 60 | 45720
Estructura (Azotea) | Concreto (losa, columnas) | CY | 368 | 160 | 58880
| Refuerzo de rebar | Toneladas | 55.2 | 1200 | 66240
| Encofrado | SF | 8700 | 6 | 52200
| Mano de obra | Horas | 600 | 60 | 36000
Total General |  |  |  |  | 9558650
Tabla de Dimensiones
Piso/Nivel | Altura (ft) | Ancho (ft) | Largo (ft) | GSF (sq. ft.) | Notas
Sitio/Lote | N/A | 100 | 200 | 20000 | Tamaño general del lote; isla artificial con alto nivel freático.
Piso 1 | 20 | 75 | 175 | 13125 | Vestíbulo, retail, mikvah; área común reducida.
Piso 2 | 12 | 90 | 175 | 15750 | Sinagoga.
Pisos 3-5 | 8.25 | 90 | 175 | 15,750 cada uno (47,250 total) | Estacionamiento con EV/ADA.
Piso 6 | 10 | 70 | 155 | 10850 | Suites de hospitalidad + gimnasio (2,000 SF reducido).
Pisos 7-14 | 10 | 70 | 155 | 10,850 cada uno (86,800 total) | Condominios residenciales.
Pisos 15-22 | 10 | 60 | 145 | 8,700 cada uno (69,600 total) | Residencial/hospitalidad mixta.
Piso 23 | 13.25 | 60 | 145 | 8700 | Penthouse.
Azotea | N/A | 60 | 145 | 8700 | Piscina/spa/restaurante.
Altura Total del Edificio | 240 | - | - | - | Desde el suelo hasta la azotea; cumple con zonificación.
Beschreibung der Arbeit für den Auftragnehmer "Carlos" (Deutsch)
Als Auftragnehmer für den NeVo Tower, einem 24-stöckigen gemischt genutzten Luxus-Kondominium in North Bay Village, FL, liegt Ihr Umfang auf der Ausführung der harten Kosten. Dies umfasst die Geländevorbereitung (Räumung von 20.000 SF, Nivellierung, Ausgrabung bis 20-40 ft mit Stützung in sandigen Böden, Bodenuntersuchungen und Entwässerung für ~10 Wochen); Fundamentarbeiten (Einbau von 70 gebohrten Pfählen bis 20-40 ft, Gießen von 3.920 CY 8.000 psi Beton, Verlegung von 392 Tonnen Bewehrung und Schalung für 20.000 SF); Schubwände und Schächte (Gießen von 1.800 CY Beton mit variablen Aufzugs-Konfigurationen—3 volle Aufzüge von Etagen 1-24, 2 kommerzielle von 1-5, 1 von 1-2—plus 270 Tonnen Bewehrung und Schalung für 70.600 SF); rohe unterirdische Versorgungsleitungen (Anschluss von Wasser-, Abwasser-, Regenwasser- und Gasleitungen mit Graben von 20.000 SF); und Strukturbau (Betrieb von 2 50-Tonnen-Kränen für 20 Wochen, Einbau von 230 vorgefertigten Säulen, Gießen von 8.700 CY Beton für 10"-Platten in Etagen 2-23 und Dach, Verlegung von 1.305 Tonnen Bewehrung und Schalung für 260.685 SF). Alle Arbeiten entsprechen dem Florida Building Code und Miami-Dade-Standards, mit Fokus auf Küstenresilienz und Luxusausstattung über 36 Monate ab Q3 2026.
Tabelle des Budget-Despegue (Fokus auf Struktur, Durchschnittspreise)
Kategorie | Artikel | Einheit | Menge | Einheitspreis (Durchschnitt Miami 2025) | Gesamtkosten
Geländevorbereitung | Räumung und Nivellierung des Geländes | SF | 20000 | 1.5 | 30000
| Ausgrabung | SF | 20000 | 2.5 | 50000
| Bodenuntersuchungen und geottechnisch | Lot | 1 | 50000 | 50000
| Entwässerung | Lot | 1 | 100000 | 100000
Fundament | Gebohrte Pfähle/Caissons | Jeder | 70 | 10000 | 700000
| Beton (Pfähle, Kappen, Balken) | CY | 3920 | 160 | 627200
| Bewehrung mit Rebar | Tonnen | 392 | 1200 | 470400
| Schalung und Stützung | SF | 20000 | 6 | 120000
Schubwände (inkl. Schächte) | Beton (Kern, Aufzüge, Treppenhäuser) | CY | 1800 | 160 | 288000
| Bewehrung mit Rebar | Tonnen | 270 | 1200 | 324000
| Schalung | SF | 70600 | 6 | 423600
Rohe Unterirdische Versorgungsleitungen | Wasserleitungsanschluss | Lot | 1 | 50000 | 50000
| Abwasserleitungsanschluss | Lot | 1 | 50000 | 50000
| Regenwasserdrainage | Lot | 1 | 75000 | 75000
| Gasleitungsanschluss | Lot | 1 | 30000 | 30000
| Graben und Verfüllung | SF | 20000 | 3 | 60000
Struktur (Kran & Arbeit) | 50-Tonnen-Kräne | Jeder | 2 | 250000 | 500000
| Vorgefertigte Säulen | Jeder | 230 | 2000 | 460000
| Beton (Platten, Etagen 2–23 + Dach) | CY | 8700 | 160 | 1392000
| Bewehrung mit Rebar | Tonnen | 1305 | 1200 | 1566000
| Schalung | SF | 260685 | 6 | 1564110
| Kranarbeit | Stunden | 1790.4 | 60 | 107424
| Platten-Gießarbeit | Stunden | 18270 | 60 | 1096200
| Säulen-Installationsarbeit | Stunden | 1840 | 60 | 110400
| Effizienzbonus | Lot | 1 | 100000 | 100000
Struktur (Etage 1) | Beton (Platte, Säulen) | CY | 605 | 160 | 96800
| Bewehrung mit Rebar | Tonnen | 90.8 | 1200 | 108960
| Schalung | SF | 13125 | 6 | 78750
| Arbeit | Stunden | 908 | 60 | 54480
Struktur (Etagen 2–23) | Beton (Platten, Säulen) | CY | 8075 | 160 | 1292000
| Bewehrung mit Rebar | Tonnen | 1211.3 | 1200 | 1453560
| Schalung | SF | 238950 | 6 | 1433700
| Arbeit (Etagen 2–5, pro Etage) | Stunden | 1350 | 60 | 81000
| Arbeit (Etagen 6–14, pro Etage) | Stunden | 932 | 60 | 55920
| Arbeit (Etagen 15–23, pro Etage) | Stunden | 762 | 60 | 45720
Struktur (Dach) | Beton (Platte, Säulen) | CY | 368 | 160 | 58880
| Bewehrung mit Rebar | Tonnen | 55.2 | 1200 | 66240
| Schalung | SF | 8700 | 6 | 52200
| Arbeit | Stunden | 600 | 60 | 36000
Gesamtsumme |  |  |  |  | 9558650
Tabelle der Dimensionen
Etage/Ebene | Höhe (ft) | Breite (ft) | Länge (ft) | GSF (sq. ft.) | Notizen
Gelände/Lot | N/A | 100 | 200 | 20000 | Gesamte Lot-Größe; künstliche Insel mit hohem Grundwasserstand.
Etage 1 | 20 | 75 | 175 | 13125 | Lobby, Retail, Mikvah; reduzierte Gemeinschaftsfläche.
Etage 2 | 12 | 90 | 175 | 15750 | Synagoge.
Etagen 3-5 | 8.25 | 90 | 175 | 15,750 je (47,250 total) | Parken mit EV/ADA.
Etage 6 | 10 | 70 | 155 | 10850 | Hospitality-Suiten + Fitnessstudio (2,000 SF reduziert).
Etagen 7-14 | 10 | 70 | 155 | 10,850 je (86,800 total) | Residential-Kondominien.
Etagen 15-22 | 10 | 60 | 145 | 8,700 je (69,600 total) | Gemischte Residential/Hospitality.
Etage 23 | 13.25 | 60 | 145 | 8700 | Penthouse.
Dach | N/A | 60 | 145 | 8700 | Pool/Spa/Restaurant.
Gesamthöhe des Gebäudes | 240 | - | - | - | Vom Boden bis zum Dach; konform mit Zonierung.
Best regards,
Eli (Managing Member, Tykun Luxury Ltd.)

## File list - list of pros - budg
NeVo Tower Project Files (Root Folder)
Overviews and Introductions
Project_Overview.docx (paste the latest overview text)
Partners_Not_Paychecks_Introduction.docx (paste the model description)
Budgets and Costs
Hard_Costs_Budget.xlsx (export the budget tables to Excel)
Insurance_Budget.xlsx (paste the insurance table)
Takeoffs and Scopes
Structure_Takeoff.xlsx (paste the takeoff table)
Scope_of_Work.docx (paste the SOW details)
Contractor_Description_Carlos_Multilingual.docx (paste the work description in 3 languages)
Analyses and Ratios
SF_Ratios_Analysis.docx (paste the square footage analysis)
Dimensions and Tables
Site_Dimensions_Table.xlsx (paste the dimensions table)
Revisions and Archives
Old_Version_Overview_2025-07-15.docx (for previous iterations)
Chat_Transcripts.txt (copy full conversation threads for context)
Professionals for Hard Costs
Category | Professionals Needed | Roles/Notes
Site Preparation & Foundation | Civil Engineer, Geotechnical Engineer, Excavation Contractor, Piling Specialist, Surveyor | Civil engineer designs drainage/site layout, ensures flood resilience; geotech analyzes soil (critical in sandy/high-water-table NBVsouthcoastimprovement.com); contractor excavates; specialist installs piles; surveyor maps.
Structure & Exterior (Frame, Roof, Envelope) | Structural Engineer, General Contractor, Concrete Specialist, Facade Installer, Crane Operator | Structural engineer certifies frame against hurricanes; contractor oversees; specialist pours concrete; installer handles facade/windows; operator runs cranes.
Interiors & Finishes | Interior Designer, Carpenter, Painter, Flooring Installer, Millwork Specialist | Designer plans luxury layouts; carpenter/millworker builds custom elements; painter/floorer applies finishes.
Mechanical, Electrical, Plumbing (MEP) | Mechanical Engineer, Electrical Engineer, Plumbing Engineer, HVAC Technician, Electrician, Plumber, Fire Safety Engineer | Engineers design systems; technicians install; fire safety engineer ensures code-compliant suppression/alarms (e.g., NFPA standards in FL Fire Prevention Codefloridabuilding.orgnassaucountyfl.com).
Landscaping & Exterior Amenities | Landscape Architect, Landscaper, Pool Contractor, Gym Equipment Installer | Architect designs sustainable exteriors; contractor builds pool/gym; landscaper plants.
Professionals for Soft Costs
Category | Professionals Needed | Roles/Notes
Design & Engineering (Architect, Engineer) | Architect, Structural Engineer, MEP Engineer, Value Engineer, Civil Engineer | Architect leads blueprints; engineers handle structural/MEP/civil aspects (e.g., site utilitiesinnodez.com); value engineer optimizes costs.
Permitting & Fees | Permitting Specialist, Zoning Lawyer, Environmental Consultant | Specialist submits plans; lawyer navigates FL Building Code variances; consultant assesses impacts (e.g., stormwater for waterfront).
Marketing & Sales | Marketing Specialist, Real Estate Broker, Graphic Designer | Specialist targets luxury buyers; broker manages sales; designer creates materials.
Legal & Insurance | Lawyer, Insurance Broker | Lawyer drafts agreements; broker secures coverage (e.g., $2M liability for high-riseestimatorflorida.com).
Project Management & Overhead | Project Manager, Owners' Representative, IT Specialist | Manager coordinates; rep oversees partners; specialist implements AI/tools.
Contingencies & Miscellaneous | Risk Analyst, Accountant, Fire Safety Engineer (for inspections) | Analyst plans buffers; accountant tracks; fire engineer conducts milestone safety checks (required every 10 years for high-risesdestefanoengineering.com+4 more).
Category | Sub-Category | Amount | Percentage of $77M | Notes
Hard Costs (Direct Construction) |  | 59500000 | 77.3% | Core building expenses, reduced via in-kind materials/labor.
Site Preparation & Foundation | 12000000 | 15.6% | Excavation, piling, utilities connection; waterfront site adds resilience costs.
Structure & Exterior (Frame, Roof, Envelope) | 15000000 | 19.5% | Concrete/steel framing for 24 stories, facade, windows; ~$57/GSF.
Interiors & Finishes | 15000000 | 19.5% | Unit build-outs, common areas, amenities (pool, gym); luxury specs.
Mechanical, Electrical, Plumbing (MEP) | 14500000 | 18.8% | HVAC, elevators, fire systems; energy-efficient for fee reductions.
Landscaping & Exterior Amenities | 3000000 | 3.9% | Rooftop pool/spa, parking garage finishes.
Soft Costs (Indirect/Supporting) |  | 17500000 | 22.7% | Planning, fees, overhead; expedited processes lower some.
Design & Engineering (Architect, Engineer) | 4000000 | 5.2% | Plans, RFQ responses; in-kind from super team.
Permitting & Fees | 3000000 | 3.9% | Reduced 15% via amenities; site plan review, impact fees.
Marketing & Sales | 3000000 | 3.9% | Pre-sales, broker fees; targets Jewish/luxury buyers.
Legal & Insurance | 3000000 | 3.9% | Contracts, liability; partner contributions.
Project Management & Overhead | 1500000 | 1.9% | GP oversight, AI tools, owners' rep.
Contingencies & Miscellaneous | 3000000 | 3.9% | 8% buffer for overruns, inflation; includes potential bridge if agreed.
Total |  | $77M | 100% | Aligned with $350-500/GSF Miami-Dade averages, post-20% in-kind savings.
Interiors & Finishes Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
Drywall Installation | SF | 417240 | 5 | 2086200 | Walls and ceilings; 2x NSF for double-sided coverage.
Flooring (Tile, Carpet, Hardwood) | SF | 208620 | 8 | 1668960 | Usable NSF; luxury mix for units and common areas.
Paint and Wall Finishes | SF | 417240 | 1 | 417240 | Interior surfaces; high-end paints and textures.
Cabinets and Millwork | Units | 75 | 15000 | 1125000 | Kitchen/bath cabinets per residential unit; custom luxury.
Doors and Hardware | Each | 375 | 500 | 187500 | Interior doors (5 per unit average for 75 units).
Fixtures (Lighting, Plumbing Trim) | Each | 225 | 1000 | 225000 | 3 per unit for luxury accents in baths/kitchens.
Amenities Finishes (Gym, Pool Area) | SF | 8960 | 30 | 268800 | Gym (2,000 SF) + pool (6,960 SF); specialized waterproofing/tile.
Total |  |  |  | 5978700
Mechanical, Electrical, Plumbing (MEP) Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
HVAC Systems (Ductwork, Units) | LB | 130388 | 3 | 391164 | Ducts at 0.5 lb/sf NSF; central units for 75 residential + amenities.
Electrical Wiring and Panels | FT | 260775 | 1 | 260775 | Wiring at 1 ft/sf NSF; panels for units/common areas.
Plumbing Pipes and Fixtures | FT | 130388 | 1.5 | 195582 | Pipes at 0.5 ft/sf NSF; fixtures for 75 units (kitchens/baths).
Elevators | Each | 6 | 500000 | 3000000 | Variable: 3 full (1-24), 2 commercial (1-5), 1 short (1-2).
Fire Suppression Systems | SF | 260775 | 5 | 1303875 | Sprinklers and alarms across GSF.
Low-Voltage Systems (Security, AV) | Units | 75 | 5000 | 375000 | Per unit; luxury smart home integration.
Total |  |  |  | 5526396
Landscaping & Exterior Amenities Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
Landscaping (Plants, Soil) | CY | 2000 | 50 | 100000 | Soil/plants for rooftop and ground-level green areas.
Paving and Decking | SF | 15000 | 15 | 225000 | Walkways, pool deck, parking finishes.
Pool and Spa Installation | SF | 6960 | 100 | 696000 | Rooftop pool with Dead Sea float mini-spa.
Gym Equipment and Flooring | SF | 2000 | 150 | 300000 | Interior gym finishes and equipment.
Exterior Lighting and Irrigation | Each | 50 | 2000 | 100000 | Fixtures and systems for amenities/parking.
Total |  |  |  | 1421000
Design & Engineering (Architect, Engineer) Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
Architectural Design Plans | Lot | 1 | 1500000 | 1500000 | Full blueprints, 3D models for 260,775 GSF.
Engineering (Structural, MEP) | Lot | 1 | 2500000 | 2500000 | Calculations, RFQ responses for super team.
Value Engineering Reviews | Each | 3 | 100000 | 300000 | Optimizations for cost savings (pre, mid, post-design).
Total |  |  |  | 4300000
Permitting & Fees Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
Site Plan Approval | Lot | 1 | 500000 | 500000 | Submission and review for zoning/impact.
Building Permits | Lot | 1 | 1000000 | 1000000 | For construction, reduced 15% via amenities.
Impact and Utility Fees | Lot | 1 | 500000 | 500000 | Environmental, traffic fees for high-rise.
Total |  |  |  | 2000000
Marketing & Sales Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
Pre-Sales Campaigns | Lot | 1 | 1000000 | 1000000 | Digital/marketing for cash partners and general sales.
Broker Engagements | Each | 20 | 50000 | 1000000 | Commissions/fees for 75 units.
Virtual Tours and Materials | Lot | 1 | 500000 | 500000 | 3D renders, brochures for luxury buyers.
Total |  |  |  | 2500000
Legal & Insurance Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
Contracts and Agreements | Lot | 1 | 1000000 | 1000000 | Partnership docs, vendor contracts.
Liability Insurance | Lot | 1 | 1500000 | 1500000 | Coverage during construction ($2M min).
Legal Reviews | Each | 5 | 100000 | 500000 | For permitting, zoning, disputes.
Total |  |  |  | 3000000
Project Management & Overhead Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
GP Oversight and AI Tools | Lot | 1 | 500000 | 500000 | Real-time tracking, remote cameras.
Owners' Rep Services | Lot | 1 | 500000 | 500000 | Partner representation for audits.
Administrative Overhead | Months | 36 | 27778 | 1000000 | Office, utilities during construction.
Total |  |  |  | 2000000
Contingencies & Miscellaneous Takeoff and Budget
Item | Unit | Quantity | Unit Cost | Total Cost | Notes
Inflation Buffer | Lot | 1 | 1000000 | 1000000 | 8% for material/labor increases.
Unforeseen Overruns | Lot | 1 | 1000000 | 1000000 | Weather, delays in hurricane zone.
Miscellaneous (Tests, Minor Items) | Lot | 1 | 1000000 | 1000000 | Additional surveys, small changes.
Total |  |  |  | 3000000
Total Summary
Hard Costs (Interiors & Finishes + MEP + Landscaping & Exterior Amenities): $12,926,096
Soft Costs (Design & Engineering + Permitting & Fees + Marketing & Sales + Legal & Insurance + Project Management & Overhead + Contingencies & Miscellaneous): $16,800,000
Grand Total: $29,726,096 (Note: This is a subset; full hard/soft totals $77M as per spreadsheet).
Standard Process for Building a High-Rise Tower
Building a high-rise tower (typically defined as buildings over 75-100 ft or 7-10 stories, per CTBUH criteria) follows a structured process used by developers worldwide, adapted for local regulations like those in Florida (e.g., hurricane resilience in Miami-Dade). Based on industry standards from sources like Autodesk, Wikipedia, and construction guides, the process is divided into major phases with categories, steps, and key items. This ensures safety, efficiency, and compliance with codes (e.g., Florida Building Code for structural loads and fire safety).
Phase | Major Categories | Key Steps and Items
Preconstruction/Development | Project Feasibility & Planning | - Site selection and acquisition (e.g., geotechnical soil testing for high water table in areas like North Bay Village).autodesk.comcalalaw.com - Market analysis and budgeting (e.g., pro forma for $91M costs, revenue projections).hawaiibusiness.com - Assembling team (architects, engineers, contractors; RFQs for super team).jrmcm.com - Financing and partnerships (e.g., in-kind contributions in "Partners Not Paychecks" model). Items: Due diligence reports, initial surveys. Duration: 6-18 months.
Design & Permitting | Architectural & Engineering Design | - Conceptual design (blueprints, 3D models for 260,775 GSF).en.wikipedia.org - Detailed engineering (structural, MEP, civil for foundation/piles; fire safety for sprinklers/alarms).zarea.pkacco.com.pk - Zoning/permitting (site plan approval, impact fees reduced 15% via amenities like synagogue).autodesk.comzarea.pk Items: Value engineering, environmental assessments. Duration: 6-12 months (fast-track possible in Miami-Dade).
Site Preparation & Foundation | Groundwork & Substructure | - Clearing/excavation (20,000 SF lot, dewatering for high water table).youtube.comacco.com.pk - Foundation (70 piles, 3,920 CY concrete for resilience).en.wikipedia.org Items: Shoring, utilities rough-in. Duration: 3-6 months.
Construction Phase | Superstructure & Building | - Frame erection (pre-cast columns/slabs for floors 2-23, cast-in-place floor 1).youtube.comen.wikipedia.org - MEP installation (HVAC, electrical, plumbing, elevators).autodesk.com - Interiors/finishes (drywall, flooring, amenities like pool/gym).autodesk.com - Exterior/landscaping (facade, rooftop).acco.com.pk Items: Cranes, safety inspections. Duration: 24-30 months.
Post-Construction | Closeout & Occupancy | - Final inspections/testing (Certificate of Occupancy, warranties).autodesk.comjrmcm.com - Punch list resolutions, handover to owners/HOA.autodesk.com - Marketing/sales completion. Items: As-built drawings, maintenance plans. Duration: 3-6 months.
Overall timeline: 3-5 years, with overlaps. Costs: Hard ~77% ($59.5M), soft ~23% ($17.5M). Risks like hurricanes require contingencies. For NeVo, the cooperative model accelerates via in-kind contributions
Unit Costs: These are based on my research for average 2025 Miami construction prices, not your sheet (which has aggregate sub-budgets like $15M for Structure but no unit breakdowns). Research sources include RSMeans, Gordian Construction Costs, ENR (Engineering News-Record) data, and FL-specific reports (e.g., Miami-Dade averages adjusted for 3-5% inflation from 2024, waterfront premiums ~10-20% for resilience). Examples:
Concrete: $160/CY (RSMeans 2024 Miami avg. $150, +6% inflation).
Rebar: $1,200/ton (ENR 2024 steel avg. $1,100/ton, +9% for FL supply chain).
Formwork: $6/SF (Gordian 2025 estimate $5-7/SF for reusable high-rise forms).
Labor: $60/hr (Miami union avg. for skilled trades, per BLS 2024 +5% projection).
Cranes: $250,000 each (20-week rental; EquipmentWatch data for 50-ton in FL).
Total Costs: Estimations from Quantity x Unit Cost, scaled to fit within your sheet's sub-budgets (e.g., Structure ~$15M aggregate; my takeoff totals $9.6M to leave room for contingencies/labor scaling). Differences are intentional for conservatism—research shows costs can vary 10-20% based on bids, so these are mid-range averages.
If any unit cost seems off or you have specific sources/prices, provide them for recalibration!
Key Item Example | Quantity (From Sheet/Takeoff) | Unit Cost (Research Est.) | Total Cost (Calculated) | Research Basis
Concrete (Slabs) | 8,700 CY | 160 | 1392000 | RSMeans/ENR 2025 Miami avg. for pumped 8,000 psi.
Rebar | 1,305 tons | 1200 | 1566000 | ENR steel pricing + FL tariff adjustments.
Formwork | 260,685 SF | 6 | 1564110 | Gordian high-rise formwork rates.
Labor (Slab Pouring) | 18,270 hours | 60 | 1096200 | BLS Miami skilled labor avg. + inflation.
Cranes | 2 each | 250000 | 500000 | EquipmentWatch rental rates for 50-ton in FL.
Phase | Categories
Pre-Development | Project Initiation, Feasibility Analysis, Legal and Financial Setup, Permitting and Approvals
Design and Planning | Architectural Design, Structural Engineering, Sustainability and Innovation
Pre-Construction | Project Management, Marketing and Sales Preparation, Insurance and Risk Management
Construction | Site Preparation and Foundation, Structural Construction, Interiors and Finishes, MEP Installation, Sales and Marketing Execution
Post-Construction | Sales Completion, Financial and Legal Closeout, Operational Transition